## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001957/2022-2023 | 860/W/MMD | 27/03/2023 | 23/09/2023 | SUBHASIS ROY | 23.7 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Mukutshila Zone-I PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division,PHE Dte. Purba Medinipur. (Length-60.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000615/2023-2024 | 2277/TD | 07/09/2023 | 22/10/2023 | SAMIT KUMAR MONDAL | 8.63 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 1194/TD | 06/09/2022 |  | Resource Division | 108.25 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Way Leave permission from South Eastern Railway for Mukutshilla Zone-I PWSS for Application ID-SER-KGP-2023-WL-57 |  |  | BILL/01830/2023-2024 | BP-2023-24-824 | 22/01/2024 |  | FA & CAO, S.E. RAILWAY, GRC. | 5.27 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with Construction of R.C.C. Elevated Reservoir of Capacity 600 Cum and Staging Height of 20.0 Mtr. as per departmental drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000411/2022-2023 | 1575/TD | 14/10/2022 | 12/04/2023 | GEE BEE NIRMAN CO PVT LTD. | 796.53 | 92.06 | 11.56 | 48
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Rising main and other allied works Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000589/2023-2024 | 2190/TD | 01/09/2023 | 01/10/2023 | GRAND CONSTRUCTION | 11.85 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Construction of 3.60 mtr x 3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary and water supply arrangements including Plinth Protection at 3rd TW site for Mukutshila Zone-I water supply scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) | Assistant Engineer | Junior Engineer | ORD/000724/2023-2024 | 2968/TD | 28/11/2023 | 27/01/2024 | ABHIJIT BERA | 3.72 | 2.15 | 57.83 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Construction of Temporary 25(twenty five) nos. Latrine & Urinal for Krishnanagar Matrisakti Aradhana Mela at Krishnanagar within Khejuri-I Block in the year 2023, under Contai sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PART-B) Date of Mela :- 20.03.2023 to 23.03.2023,(4 days) | Assistant Engineer | Junior Engineer | ORD/000999/2022-2023 | 395/CSD | 16/03/2023 | 19/03/2023 | M/S. NEW DINDA ENTERPRISE | 0.62 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Temporary water supply arrangement through pipe line & PVC tank connection from distribution pipe line of Mukutshila Zone-I W/S Scheme for Krishnanagar Matrisakti Aradhana Mela at Krishnanagar within Khejuri-I Block in the year 2023, under Contai sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PART-A), Date of Mela :- 20.03.2023 to 23.03.2023, (4 days) | Assistant Engineer | Junior Engineer | ORD/000998/2022-2023 | 394/CSD | 16/03/2023 | 19/03/2023 | M/S. NEW DINDA ENTERPRISE | 0.7 | 0.26 | 36.69 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | payment Wayleave plan & survey charges SER-KGP-2024-WL-103 |  |  | BILL/00486/2024-2025 | BP-2024-25-189 | 14/06/2024 |  | FA & CAO, S.E. RAILWAY, GRC. | 0.1 | 0 | 0 | null
11 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | payment Wayleave plan & survey charges SER-KGP-2024-WL-103 |  |  | BILL/00486/2024-2025 | BP-2024-25-189 | 14/06/2024 |  | FA & CAO, S.E. RAILWAY, GRC. | 0.1 | 0 | 0 | null
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Quotation for new service connection at Mukutshila Zone I w/s scheme PH III Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004671631, Ref ID 204266595) |  |  | BILL/01314/2024-2025 | null | 09/04/2024 |  | WBSEDCL | 4.59 | 0 | 0 | null
13 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10591 | Augmentation | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-103) |  |  | BILL/00694/2024-2025 | BP-2024-25-301 | 30/07/2024 |  | FA & CAO, S.E. RAILWAY, GRC. | 5.75 | 0 | 0 | null
Total | [13 empty] | 969.81 | 94.47 | 9.74