## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Retrofitting to accommodate of 1410 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-B) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000261/2022-2023 | 1078/TD | 23/08/2022 | 07/10/2022 | SWADHIN KUMAR CHAKRABORTY | 241.76 | 159.66 | 66.04 | 95
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Payment to WBSEDCL for Quotation Money of Pump House No. ¿ III of Khejuri Zone-I PWSS under Tamluk Division, PHE Dte. |  |  | BILL/01305/2023-2024 | BP-2023-24-583 | 22/11/2023 | 22/11/2023 | WBSEDCL | 2.88 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001962/2022-2023 | 861/W/MMD | 27/03/2023 | 23/09/2023 | DIAMOND ELECTRICAL WORKS | 13.43 | 12.63 | 94.01 | 95
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-S) | Assistant Engineer | Junior Engineer | ORD/000469/2023-2024 | 1450/TD | 13/07/2023 | 12/08/2023 | DEBABRATA DAS | 9.42 | 6.64 | 70.45 | 70
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-O) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000893/2023-2024 | 247/TD | 11/01/2024 | 31/01/2024 | GITA ENTERPRISE | 9.75 | 6.62 | 67.94 | 90
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 1st Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 2nd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000312/2022-2023 | 1225/TD | 07/09/2022 | 17/10/2022 | M/S SYCHROTECH INDUSTRY | 71.86 | 15.76 | 21.93 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Repairing of existing Store Room with Guard Room with sanitary & water supply arrangements including Plinth Protection of OHR Site under Augmentation of Khejuri Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000767/2022-2023 | 2770/TD | 09/02/2023 | 11/03/2023 | GIRI CONSTRUCTION | 9.94 | 9.82 | 98.77 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Laying of distribution pipe line and Rising main, construction of boundary wall and construction of Switch Room with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000539/2023-2024 | 1838/TD | 08/08/2023 | 17/09/2023 | SK. SARFARAJ | 16.93 | 13.3 | 78.61 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Retrofitting to accommodate of 200 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-L) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000891/2023-2024 | 246/TD | 11/01/2024 | 05/02/2024 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.96 | 42.14 | 98.08 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of Barka saria Mouja under Khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000854/2023-2024 | 67/TD | 05/01/2024 | 12/01/2024 | AMITAVA MONDAL | 0.96 | 0.95 | 98.91 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of Khejuri Mouja under Khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000855/2023-2024 | 68/TD | 05/01/2024 | 12/01/2024 | TECHNO ENTERPRISE. | 0.96 | 0.95 | 98.49 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Laying of distribution pipe line to accommodate FHTC (1557 Nos)with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-A) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000744/2022-2023 | 2551/TD | 24/01/2023 | 01/08/2025 | TARUN KOLEY | 289.69 | 203.04 | 70.09 | 70
13 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Khejuri Zone-I PWSS within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) |  |  | ORD/000480/2024-2025 | 3769/TD | 10/12/2024 | 19/01/2025 | GIRI CONSTRUCTION | 3.96 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Retrofitting to accommodate of 66 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-Q) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000185/2022-2023 | 796/TD | 12/07/2022 | 07/03/2025 | SUSANTA KUMAR KAR | 9.24 | 0 | 0 | 99
15 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) | SM/10592 | Augmentation | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000897/2023-2024 | 244/TD | 11/01/2024 | 24/12/2024 | ROY BISWAS CONSTRUCTION | 37.4 | 34.37 | 91.88 | 100
Total | [13 empty] | 761.15 | 505.88 | 66.46