## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chaitanyapur (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000458/2021-2022 | 1662/TD | 21/01/2022 | 10/02/2022 | RADIANT | 4.13 | 4.13 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (82 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-M) | Assistant Engineer | Junior Engineer | ORD/000161/2022-2023 | 737/TD | 04/07/2022 | 19/07/2022 | MAHAPRABHU ENTERPRISE | 10.01 | 9.87 | 98.65 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (500 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000154/2022-2023 | 729/TD | 04/07/2022 | 29/07/2022 | ZENITH CONSTRUCTION | 80.53 | 78.32 | 97.25 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (840 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000152/2022-2023 | 727/TD | 04/07/2022 | 29/07/2022 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 70.64 | 64.02 | 90.64 | 95
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (115 nos) work within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-O) | Assistant Engineer | Junior Engineer | ORD/000163/2022-2023 | 739/TD | 04/07/2022 | 19/07/2022 | CANVAS | 9.54 | 4.82 | 50.58 | 55
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (350 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-H) | Assistant Engineer | Junior Engineer | ORD/000165/2022-2023 | 732/TD | 04/07/2022 | 24/07/2022 | SK MAIDUL ISLAM | 40.03 | 32.28 | 80.63 | 85
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 4th Tube Well site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000660/2022-2023 | 2345/TD | 10/01/2023 | 19/02/2023 | TAPAN BERA | 5.08 | 5.06 | 99.58 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (50 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000141/2022-2023 | 715/TD | 28/06/2022 | 18/07/2022 | SANTANU PATTANAYAK | 4.27 | 4.21 | 98.65 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Chaitanyapur Zone -I Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000410/2022-2023 | 1564/TD | 12/10/2022 | 26/11/2022 | SAYAN MAITY | 3.95 | 3.93 | 99.44 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase - 2) Name of Work site :- 1) Chaitanyapur Zone-I (Part-A) PWSS, 2) Chaitanyapur Zone-I (Part-B) PWSS, 3) Chaitanyapur Zone-I (Part-C) PWSS, 4) Chaitanyapur Zone-I (Part-D) PWSS, 5) Chaitanyapur Zone-I (Part-E) PWSS, 6) Chaitanyapur Zone-I (Part-F) PWSS, 7) Chaitanyapur Zone-I (Part-G) PWSS & 8) Chaitanyapur Zone-I (Part-H) PWSS | Assistant Engineer | Junior Engineer | ORD/000439/2022-2023 | 724/HSD | 28/10/2022 | 31/10/2022 | TAPAN BERA | 0.93 | 0.93 | 100 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase -3) Name of Work site :- 1) Chaitanyapur Zone-I (Part-I) PWSS, 2) Chaitanyapur Zone-I (Part-J) PWSS, 3) Chaitanyapur Zone-I (Part-K) PWSS, 4) Chaitanyapur Zone-I (Part-L) PWSS, 5) Chaitanyapur Zone-I (Part-M) PWSS, 6) Chaitanyapur Zone-I (Part-N) PWSS, 7) Chaitanyapur Zone-I (Part-O) PWSS & 8) Chaitanyapur Zone-I (Part-P) PWSS | Assistant Engineer | Junior Engineer | ORD/000440/2022-2023 | 725/HSD | 28/10/2022 | 31/10/2022 | TAPAN BERA | 0.93 | 0.93 | 100 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Construction of Boundary Wall at 1st tube well site of Chaitanyapur Zone-I water supply scheme, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000802/2022-2023 | 910/HSD | 23/02/2023 | 05/03/2023 | MODERN CONSTRUCTION | 0.95 | 0.92 | 96.8 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (110 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-P) | Assistant Engineer | Junior Engineer | ORD/000164/2022-2023 | 740/TD | 04/07/2022 | 19/07/2022 | TARUN KHATUA | 10.01 | 10 | 99.89 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 467/TD | 02/06/2022 | 02/06/2022 | Resource Division | 10.8 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 466/W | 02/06/2022 | 02/06/2022 | Resource Division | 40.61 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 468/W | 02/06/2022 | 02/06/2022 | Resource Division | 30.41 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 829/TD | 15/07/2022 | 15/07/2022 | Resource Division | 55.98 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-IV, zone- I, (Ref. ID-204078116) |  |  | BILL/02605/2023-2024 | BP-2023-24-249 | 19/09/2023 | 19/09/2023 | WBSEDCL | 10.52 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (200 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-I) | Assistant Engineer | Junior Engineer | ORD/000157/2022-2023 | 733/TD | 04/07/2022 | 14/04/2026 | R CONSTRUCTION | 20.34 | 15.02 | 73.84 | 78
20 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Construction of Boundary Wall at 1st tube well site of Chaitanyapur Zone-I water supply scheme, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000801/2022-2023 | 909/HSD | 23/02/2023 | 05/03/2023 | RAI CONSTRUCTION | 0.95 | 0.92 | 97.44 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Canal crossing and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte (PART - J). | Assistant Engineer | Junior Engineer | ORD/000856/2022-2023 | 3209/TD | 14/03/2023 | 03/04/2023 | TAPAN BERA | 8.74 | 8.72 | 99.69 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Earth filling and Making approach road at OHR site at Chaitanyapur (Zone-I) Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of approach road -45mtr) | Assistant Engineer | Junior Engineer | ORD/000593/2023-2024 | 2208/TD | 01/09/2023 | 03/01/2025 | BAGLAMUKHI SECURITY SERVICE | 8.55 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (460 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000153/2022-2023 | 728/TD | 04/07/2022 | 29/07/2022 | NARAYAN MANDAL | 80.94 | 77.3 | 95.5 | 100
24 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (96 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-L) | Assistant Engineer | Junior Engineer | ORD/000160/2022-2023 | 736/TD | 04/07/2022 | 19/07/2022 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 10 | 9.57 | 95.68 | 100
25 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head Work Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 2nd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000337/2022-2023 | 1250/TD | 12/09/2022 | 22/10/2022 | SIMPLEX DRILLING COMPANY | 77.68 | 20.05 | 25.81 | 100
26 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001932/2022-2023 | 851/W/MMD | 24/03/2023 | 20/09/2023 | ECO ENTERPRISE | 13.46 | 13.19 | 97.98 | 40
27 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Canal Crossing and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur Zone-I W/S Scheme under Haldia Sub-Division of Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000359/2023-2024 | 927/TD | 01/06/2023 | 01/07/2023 | NARAYAN MANDAL | 7.82 | 5.07 | 64.75 | 100
28 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Construction of Damaged bitumen road from PHE office to Rampur more at Chaitanyapur (zone-1) W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of approach road -330mtr) | Assistant Engineer | Junior Engineer | ORD/000616/2023-2024 | 2281/TD | 07/09/2023 | 27/09/2023 | RAI CONSTRUCTION | 9.04 | 9.01 | 99.73 | 100
29 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Construction of boundary wall, Retaining wall, Approach road & Earth filling Work in 4th tubewell site of Chaitanyapur Zone-I Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) , (length of Retaining wall-13mtr) & (length of Approach road-20mtr). | Assistant Engineer | Junior Engineer | ORD/000572/2023-2024 | 2163/TD | 31/08/2023 | 30/09/2023 | TAPAN BERA | 13.62 | 9.27 | 68.07 | 100
30 | PURBA MEDINIPUR |  | Central Drilling | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 280 Mtrs. Depth) by utilizing Departmental Machineries for Chaitanyapur W/S Scheme (Z-I, T/W-IV), SutahataBlock underPurbaMedinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000225/2023-2024 | 1390/CDD | 19/09/2023 | 31/05/2024 | MENAKA ENTERPRISE | 21.16 | 20.24 | 95.66 | 100
31 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Quotation bill for new service connection at Z-I of TW-III of Chaitanyapur w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695240 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-11900W |  |  | BILL/00650/2024-2025 | BP-2024-25-114 | 06/05/2024 | 06/05/2024 | WBSEDCL | 7.14 | 0 | 0 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (104 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-N) | Assistant Engineer | Junior Engineer | ORD/000162/2022-2023 | 738/TD | 04/07/2022 | 05/06/2026 | MODERN CONSTRUCTION | 10 | 6.81 | 68.1 | 100
33 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (850 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 700 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000244/2022-2023 | 1004/TD | 08/08/2022 | 01/01/2026 | HARIPADA PATTANAYAK | 212.75 | 87.96 | 41.34 | 80
34 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Laying left out pipe line and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur (Zone-I) Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000636/2023-2024 | 2448/TD | 20/09/2023 | 21/01/2026 | S.D. CONSTRUCTION | 69.7 | 31.16 | 44.71 | 40
35 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Laying Rising main work of ground water based Chaitanyapur (Zone-I) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000580/2023-2024 | 2202/TD | 01/09/2023 | 21/09/2023 | ELECTIVA ENTERPRISE | 6.04 | 1.1 | 18.21 | 40
36 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (200 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-J) | Assistant Engineer | Junior Engineer | ORD/000158/2022-2023 | 734/TD | 04/07/2022 | 10/06/2025 | TAPAN BERA | 20.46 | 18.17 | 88.83 | 100
37 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (370 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer | Junior Engineer | ORD/000156/2022-2023 | 731/TD | 04/07/2022 | 09/07/2025 | MAA KALI CONSTRUCTION | 39.79 | 35.78 | 89.91 | 75
38 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (210 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-K) | Assistant Engineer | Junior Engineer | ORD/000159/2022-2023 | 735/TD | 04/07/2022 | 07/12/2024 | SUDIP MANNA | 20.03 | 18.82 | 93.96 | 95
39 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Chaitanyapur Zone-I Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000409/2022-2023 | 1563/TD | 12/10/2022 | 01/10/2024 | KRISHNENDU SEKHAR DAS | 4.78 | 0 | 0 | 100
40 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - III at CHAITANYAPUR Zone-I Water supply scheme, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001174/2023-2024 | 2611/W/MMD | 19/09/2023 | 01/12/2024 | THE GODFATHER TRADING COMPANY | 14.94 | 10.16 | 68 | 40
41 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/10593 | Augmentation | Work: Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part- F) | Assistant Engineer | Junior Engineer | ORD/000155/2022-2023 | 730/TD | 04/07/2022 | 07/02/2026 | SK. NUR ISLAM | 49.38 | 39.62 | 80.24 | 85
Total | [13 empty] | 1116.63 | 657.35 | 58.87