## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madhabpur (Balighai) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000324/2021-2022 | 1617/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.71 | 5.71 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madhabpur Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2022-2023 | 599/TD | 17/06/2022 | 07/07/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.61 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 1666/TD | 03/11/2022 | 03/11/2022 | Resource Division | 141.02 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000284/2022-2023 | 2637/TD | 02/02/2023 | 02/02/2023 | Resource Division | 15.45 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Electric Quotation for MADHABPUR Water Supply Scheme T/W-I, Zone-II (Ref. ID-204047955) |  |  | BILL/01869/2023-2024 | W/23-24/222 | 01/09/2023 | 01/09/2023 | WBSEDCL | 4.9 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000487/2022-2023 | 1909/TD | 25/11/2022 | 25/05/2025 | OSMAN SEKH | 69.99 | 16.02 | 22.89 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of MADHABPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671978/QUOT/03/48 DT. 05-04-2024 Application NO- 2004671978 Application type-New connection Consumer Id- 204266733 |  |  | BILL/00537/2024-2025 | BP-2024-25-90 | 24/04/2024 | 24/04/2024 | WBSEDCL | 1 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhabpur Zone-II Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000418/2022-2023 | 1576/TD | 14/10/2022 | 01/07/2025 | BASANTA KUMAR MAITY | 495.32 | 136.92 | 27.64 | 75
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001927/2022-2023 | 846/W/MMD | 24/03/2023 | 20/09/2023 | AHALYA ENGINEERING WORKS | 37.88 | 28.29 | 74.7 | 60
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II | SM/10594 | Augmentation | Construction of Pump House, Boundary Wall, Laying Rising main pipe line & Land development under JJM with allied work for Madhabpur (Z-II ) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000380/2023-2024 | 1024/TD | 07/06/2023 | 06/08/2023 | BASANTA KUMAR MAITY | 45.82 | 0 | 0 | 90
Total | [13 empty] | 820.7 | 190.55 | 23.22