## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II,Chandipur | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | SM/10619 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna.(Part Work Order PHASE-I) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000824/2022-2023 | 3141/TD | 09/03/2023 | 24/10/2026 | BIRBHUM INFRAPARK PRIVATE LIMITED | 5050.06 | 229.79 | 4.55 | 95
2 | PURBA MEDINIPUR | Bhagawanpur-II,Chandipur | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | SM/10619 | New | Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos)(Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. (Part Work Order PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 100/TD | 05/04/2023 | 28/09/2026 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4039.88 | 206.03 | 5.1 | 94
3 | PURBA MEDINIPUR | Bhagawanpur-II,Chandipur | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | SM/10619 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 2897/TD | 21/11/2023 | 21/11/2023 | Resource Division | 4.61 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-II,Chandipur | Tamluk Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHANDIPUR, BHAGWANPUR-II BLOCK OF PURBA MEDINIPUR OF WEST BENGAL. | SM/10619 | New | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 27/05/2024 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0 | 0
Total | [13 empty] | 9279.78 | 435.83 | 4.7