## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 60 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-K) | Assistant Engineer | Junior Engineer | ORD/000180/2022-2023 | 791/TD | 12/07/2022 | 27/07/2022 | M/S BLUE BIRD | 10.57 | 7.28 | 68.89 | 80
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 200 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-L) | Assistant Engineer | Junior Engineer | ORD/000181/2022-2023 | 792/TD | 12/07/2022 | 01/08/2022 | AHINDRA BARIK | 44.27 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 65 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-P) | Assistant Engineer | Junior Engineer | ORD/000184/2022-2023 | 795/TD | 12/07/2022 | 27/07/2022 | HYDROTECH ASSOCIATES | 9.05 | 4.57 | 50.45 | 70
4 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejuri Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/000438/2021-2022 | 1519/TD | 07/01/2022 | 27/01/2022 | ROY CHOWDHURY ASSOCIATES | 4.96 | 4.92 | 99.14 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Supply & Delivery 125 mm dia Sluice Valve for Augmentation of Khejuri Zone-I & Zone-II Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-A) (Supply at Mukutshila Store) | Assistant Engineer |  | ORD/000364/2022-2023 | 597 / CSD | 06/09/2022 | 21/09/2022 | ABHIJIT BERA | 2.46 | 2.46 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 69 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-N) | Assistant Engineer | Junior Engineer | ORD/000182/2022-2023 | 793/TD | 12/07/2022 | 27/07/2022 | GITA ENTERPRISE | 8.33 | 4.78 | 57.41 | 75
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 198 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-H) | Assistant Engineer | Junior Engineer | ORD/000178/2022-2023 | 789/TD | 12/07/2022 | 01/08/2022 | SUBHENDU HAZRA | 39.49 | 29.43 | 74.52 | 75
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 85 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-J) | Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 790/TD | 12/07/2022 | 27/07/2022 | GIRI ENTERPRISE | 20.05 | 16.08 | 80.21 | 70
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 66 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-Q) | Assistant Engineer | Junior Engineer | ORD/000185/2022-2023 | 796/TD | 12/07/2022 | 27/07/2022 | SUSANTA KUMAR KAR | 9.24 | 6.88 | 74.43 | 80
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Supply & Delivery 100 mm dia Sluice Valve for Augmentation of Khejuri Zone-I & Zone-II Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-B) (Supply at Mukutshila Store) | Assistant Engineer |  | ORD/000363/2022-2023 | 1296/TD | 13/09/2022 | 28/09/2022 | NANDY UDYOG | 3.62 | 3.62 | 100 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 220 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000173/2022-2023 | 785/TD | 12/07/2022 | 01/08/2022 | ABHIJIT BERA | 45.02 | 41.98 | 93.25 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 217 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-F) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000176/2022-2023 | 787/TD | 12/07/2022 | 01/08/2022 | PARIA ENTERPRISE | 42.11 | 34.27 | 81.39 | 85
13 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 67 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000174/2022-2023 | 786/TD | 12/07/2022 | 27/07/2022 | KAMAL KUMAR BERA | 9.5 | 9.49 | 99.88 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 81 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-I) | Assistant Engineer | Junior Engineer | ORD/000209/2022-2023 | 861/TD | 21/07/2022 | 05/08/2022 | R K CONSTRUCTION | 11.52 | 6.6 | 57.26 | 75
15 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Supply & Delivery 150mm, 200mm & 250mm dia Sluice Valve for Augmentation of Khejuri Zone-I Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-B) (Supply at Mukutshila Store) | Assistant Engineer |  | ORD/000361/2022-2023 | 1285/TD | 12/09/2022 | 27/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.37 | 4.37 | 100 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Supply & Delivery 80 mm dia Sluice Valve for Augmentation of Khejuri Zone-I Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-C) (Supply at Mukutshila Store) | Assistant Engineer |  | ORD/000362/2022-2023 | 1286/TD | 12/09/2022 | 27/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.79 | 3.79 | 100 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 80 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-M) | Assistant Engineer | Junior Engineer | ORD/000272/2022-2023 | 1082/TD | 24/08/2022 | 08/09/2022 | MUKHERJEE ENTERPRISE | 18.87 | 15.4 | 81.62 | 80
18 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 70 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-T) | Assistant Engineer | Junior Engineer | ORD/000273/2022-2023 | 1083/TD | 24/08/2022 | 08/09/2022 | GITA ENTERPRISE | 8.99 | 4.96 | 55.21 | 80
19 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 112 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-G) | Assistant Engineer | Junior Engineer | ORD/000177/2022-2023 | 788/TD | 12/07/2022 | 27/07/2022 | LAKSHMI NARAYAN ENTERPRISE | 19.61 | 19.61 | 100 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 300 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000170/2022-2023 | 784/TD | 12/07/2022 | 06/08/2022 | JASODA ENTERPRISE | 63.98 | 63.98 | 100 | 100
21 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 65 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-R) | Assistant Engineer | Junior Engineer | ORD/000186/2022-2023 | 797/TD | 12/07/2022 | 27/07/2022 | DEBABRATA DAS | 9.59 | 6.14 | 64.04 | 100
22 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 99 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-U) | Assistant Engineer | Junior Engineer | ORD/000274/2022-2023 | 1084/TD | 24/08/2022 | 08/09/2022 | SUBHRANGSHU SEKHAR GIRI | 7.86 | 2.73 | 34.66 | 70
23 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 1410 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-B) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000261/2022-2023 | 1078/TD | 23/08/2022 | 07/10/2022 | SWADHIN KUMAR CHAKRABORTY | 241.76 | 67.26 | 27.82 | 95
24 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 827/TD | 15/07/2022 |  | Resource Division | 210.14 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 1258/TD | 12/09/2022 |  | Resource Division | 31.77 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001962/2022-2023 | 861/W/MMD | 27/03/2023 | 23/09/2023 | DIAMOND ELECTRICAL WORKS | 13.43 | 0 | 0 | 95
27 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) | SM/10647 | Augmentation | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-O) | Assistant Engineer | Junior Engineer | ORD/000183/2022-2023 | 794/TD | 12/07/2022 | 27/07/2022 | S.A. ENTERPRISE | 9.73 | 0 | 0 | 0
Total | [13 empty] | 904.09 | 360.6 | 39.89