## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2021-2022 | 1160/TD | 01/12/2021 | 08/12/2021 | HORIZEN | 8.24 | 8.12 | 98.62 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBEWELL (300MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTALMACHINERIES FOR DAKSHIN GUMAI W/S SCHEME (TW-III), NANDAKUMAR BLOCK UNDER PURBA MEDINIPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000397/2022-2023 | 2118/CDD | 02/03/2023 | 01/04/2023 | PADMA ENGINEERING & CO. | 18.26 | 15.62 | 85.52 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 1257/TD | 12/09/2022 | 12/09/2022 | Resource Division | 34.11 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 1016/TD | 08/08/2022 | 08/08/2022 | Resource Division | 232.04 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Payment to WBSEDCL for Electric Quotation money of Dakshin Gumai Water Supply Scheme for Tube Well No.- III |  |  | BILL/00434/2023-2024 | BP-2023-24-218 | 02/08/2023 | 02/08/2023 | WBSEDCL | 3.12 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme Block - Nandakumar under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001964/2022-2023 | 863/W/MMD | 27/03/2023 | 23/09/2023 | PRANAB KUMAR DAS | 13.47 | 0 | 0 | 70
7 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxary Taxi) (standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Executive Engineer, Tamluk Division, PHE Dte. under Tamluk Division for the period from 12 (twelve) months, w.e.f. 01/11/2022 to 31/10/2023. | Assistant Engineer | Junior Engineer | ORD/001001/2022-2023 | 1344/TSD | 28/10/2022 | 24/06/2023 | TAPAS SANTRA | 1.14 | 2.4 | 211.41 | 75
8 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Construction of 3.6 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room for water supply scheme with Boundary Wall (as per Deptt. drawing) at 3rd Tube well site of Dakshin Gumai Pipe Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur . | Assistant Engineer, Headquaters | Junior Engineer | ORD/000732/2023-2024 | 2983/TD | 29/11/2023 | 13/01/2024 | BHOWMIK & SONS | 11.41 | 8.07 | 70.79 | 72
9 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Dismantling of existing OHR (Capacity 61550 Gallons or 341000 Ltr.) at Head work site of Dakshin Gumai Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000376/2023-2024 | 1029/TD | 07/06/2023 | 22/07/2023 | BISWAJIT BAG | 9.42 | 9.42 | 100 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 1108/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Laying of Distribution pipe line to accommodate FHTC (5547 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Dakshin Gumai Water Supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engiener | ORD/000387/2022-2023 | 1420/TD | 26/09/2022 | 01/06/2025 | ARABINDA GHOSH | 944.7 | 805.94 | 85.31 | 85
12 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Left out FHTC 402 Nos. including supplying, laying, fitting, fixing of Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials and labour for Dakshin Gumai Water Supply Scheme within Nandakumar Dev. Block under Tamluk SubDivision of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer | Junior Engiener | ORD/000279/2024-2025 | 2895/TD | 10/09/2024 | 05/09/2025 | ARABINDA GHOSH | 91.84 | 0 | 0 | 56
13 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Laying Rising Mains for Agumentation of Dakshin Gumai Water Supply Scheme under Nandakumar Block, under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engiener | ORD/000242/2024-2025 | 2682/TD | 22/08/2024 | 25/12/2024 | GHOSH ENTERPRISE | 10.8 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme. | SM/10682 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st & 2nd tube well site of Dakshin Gumai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engiener | ORD/000421/2024-2025 | 3477/TD | 06/11/2024 | 06/12/2024 | GLOBAL TRADE | 4.06 | 0 | 0 | 100
Total | [13 empty] | 1382.8 | 849.57 | 61.44