## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejurberia Water Supply Scheme under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000164/2021-2022 | 1168/TD | 01/12/2021 | 08/12/2021 | RADIANT | 8.76 | 8.65 | 98.7 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Khejurberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000725/2022-2023 | 2555/TD | 24/01/2023 | 25/03/2023 | PULAK KUMAR SAMANTA | 2.79 | 2.08 | 74.69 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Khejurberia Water Supply Scheme under Tamluk-Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000726/2022-2023 | 2556/TD | 24/01/2023 | 25/03/2023 | PULAK KUMAR SAMANTA | 5.09 | 5.09 | 100 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000389/2022-2023 | 1428/TD | 26/09/2022 | 23/10/2022 | PRANTIK DRILLING AGENCY | 49.66 | 29.84 | 60.09 | 80
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 1256/TD | 12/09/2022 | 12/09/2022 | Resource Division | 50.95 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 1015/TD | 08/08/2022 | 08/08/2022 | Resource Division | 69.9 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Payment to WBSEDCL for Quotation Money of Pump House No. - 4 of Khejurberia PWSS under Tamluk Division, PHE Dte. |  |  | BILL/00002/2023-2024 | BP-2023-24-12 | 17/04/2023 | 17/04/2023 | WBSEDCL | 3.87 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Payment to WBSEDCL for Quotation Money for Khejurberia PWSS under Tamluk Division, PHE Dte. |  |  | BILL/00610/2022-2023 | BP-2022-23-818 | 24/03/2023 | 24/03/2023 | WBSEDCL | 2.61 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Payment to Haldia Development Authority for underground LT power cable restoration work of LED Street lighting system (damaged due to laying of underground pipe line by PHE Deptt.) at Nandakumar Bazar area under Nandakumar Block. |  |  | BILL/00466/2023-2024 | BP-2023-24-238 | 09/08/2023 | 09/08/2023 | CHIEF EXECUTIVE OFFICER, HDA | 5.94 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Amount payment to PWD Road for damaged of carriage way and road flank caused due to laying of water pipe line of Khejurberia PWSS |  |  | BILL/01192/2023-2024 | BP-2023-24-565 | 07/11/2023 | 07/11/2023 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.37 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-41 of Khejurberia Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/001181/2023-2024 | 740/TD | 28/02/2024 | 19/03/2024 | DONA ASSOCIATES | 9.48 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001519/2022-2023 | 363/W/MMD | 09/03/2023 | 05/09/2023 | UNITED TRADERS | 23.68 | 22.93 | 96.86 | 60
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Khejurberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000724/2022-2023 | 2554/TD | 24/01/2023 | 25/03/2023 | RAI CONSTRUCTION | 2.8 | 2.8 | 99.8 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall & fencing work over boundary work with allied work for Khejurberia PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000850/2022-2023 | 3204/TD | 14/03/2023 | 03/12/2024 | TAPAS SANTRA | 29.62 | 0 | 0 | 30
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Left out pipe line of Providing Functional Household Tap Connection of Khejurberia water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000308/2023-2024 | 622/TD | 17/05/2023 | 16/06/2023 | TAPAS SANTRA | 77.24 | 77.23 | 100 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Restoration work at Panskura Durgachak road from Ch. 38.400 km to Ch. 38.404 Km (length-4.40 m) after laying pipe line by PHE. | Assistant Engineer |  | ORD/000712/2023-2024 | 1280/TSD | 15/09/2023 | 05/10/2023 | MIHIR SAMANTA | 2.99 | 2.99 | 100 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well sites of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000735/2022-2023 | 2553/TD | 24/01/2023 | 25/03/2023 | ANIRBAN MONDAL | 4.79 | 4.19 | 87.41 | 100
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Water supply & sanitary arrangement for Switch Room cum chlorine Room (pump House no-II) at Khejurberia PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000770/2023-2024 | 1688/TSD | 15/12/2023 | 08/01/2024 | TECHNO ENTERPRISE. | 0.96 | 0.96 | 99.92 | 100
19 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Left out pipe line of Providing Functional Household Tap Connection & construction of new drain of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engiener | ORD/000328/2024-2025 | 3268/TD | 04/10/2024 | 02/01/2025 | MISHRA ENTERPRISE | 44.78 | 4.96 | 11.08 | 100
20 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Payment to Haldia Development Authority for underground LT power cable restoration work of LED Street lighting system (damaged due to laying of underground pipe line by PHE Deptt.) at Nandakumar Bazar area under Nandakumar Block. |  |  | BILL/00892/2024-2025 | BP-2024-25-454 | 24/09/2024 | 24/09/2024 | CHIEF EXECUTIVE OFFICER, HDA | 1.31 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | SM/10684 | Augmentation | Laying of Distribution pipe line to accommodate FHTC (8284 nos) with new construction of R.C.C. Elevated Reservoir of capacity 1000cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejurberia Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000335/2022-2023 | 1279/TD | 12/09/2022 | 01/11/2025 | TAPAS SANTRA | 956.75 | 865.39 | 90.45 | 90
Total | [13 empty] | 1354.36 | 1027.12 | 75.84