## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bethkundu Water Supply Scheme under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000440/2021-2022 | 1543/TD | 11/01/2022 | 31/01/2022 | HORIZEN | 4.88 | 4.88 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000109/2022-2023 | 1673/TD | 03/11/2022 | 03/11/2022 | Resource Division | 48.38 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Culvert, Approach Road and Guard wall cum Boundery wall including land development at Headwork site of Betkundu Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000625/2023-2024 | 2367/TD | 12/09/2023 | 11/11/2023 | BABUL DAS | 55.26 | 22.24 | 40.24 | 41
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Laying of Leftout Pipeline, Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement at 4th Tube Well site, Construction new Boundary Wall at 4th Tube well site and Laying of proposed Rising main line and inter connection at Betkundu Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001215/2023-2024 | 979/TD | 13/03/2024 | 27/04/2024 | RAJ KUMAR SINGHA | 111.15 | 98.53 | 88.65 | 10
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Preparation of design based on soil test report and submission of drawing of foundation for construction of 900 cum RCC OHR at Betkundu PWSS at Mahishadal Block under Tamluk Division, PHE Dte. |  |  | ORD/000175/2024-2025 | 2087/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 4th Tube well Site of Betkundu Water Supply Scheme within mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000565/2023-2024 | 2051/TD | 25/08/2023 | 19/09/2023 | DEV & COMPANY | 20.17 | 18.97 | 94.05 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Quotation for net billing meter at Betkundu w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (Con ID - 222016853 & Application No.- 2004450537) |  |  | BILL/03722/2023-2024 | BP-2023-24-674 | 15/02/2024 | 15/02/2024 | WBSEDCL | 0.42 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | QUATATION BILL FOR BETKUNDU Water Supply scheme Tube Well no.-III Mahishadal CCC Application No.-2004625358 Ref ID.-204232822 Block-Mahishadal |  |  | BILL/04573/2023-2024 | BP-2023-24-889 | 22/03/2024 | 22/03/2024 | WBSEDCL | 4.84 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Augmentation of ground water based Betkundu Water Supply Scheme by providing Laying of Distribution pipe line, FHTC work, Construction of R.C.C. Over Head Reservoir of capacity 900 cum and staging height 20.00 mtr. and Sub-Soil Investigation within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000417/2022-2023 | 1577/TD | 14/10/2022 | 01/05/2025 | RAJ KUMAR SINGHA | 1014.31 | 744.56 | 73.41 | 68
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground water Based Betkundu Water Supply Scheme, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001928/2022-2023 | 847/W/MMD | 24/03/2023 | 05/09/2025 | MAA BHABOTARINE ENTERPRISE | 27.18 | 0 | 0 | 60
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground water Based Betkundu Water Supply Scheme | SM/11206 | Augmentation | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube well site of BETKUNDU Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001155/2023-2024 | 731/HSD, | 15/02/2024 | 14/11/2024 | NASIR ENTERPRISE | 2.81 | 0 | 0 | 100
Total | [13 empty] | 1290.35 | 889.18 | 68.91