## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sherkhanchak Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000363/2021-2022 | 1511/TD | 06/01/2022 | 26/01/2022 | SANTRA ENTERPRISE. | 3.71 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SHERKHANCHAK PWSS, BLOCK-KHEJURI -II, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000156/2022-2023 | 133/CMSD-II | 12/08/2022 | 27/08/2022 | MENAKA ENTERPRISE | 5 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN SHERKHANCHAK PWSS, ZONE-II, BLOCK-KHEJURI-II, DIST-PURBA MEDINIPUR UNDER CDD, PHE DTE. |  |  | ORD/000176/2022-2023 | 146/S&WSD | 12/08/2022 | 27/08/2022 | MENAKA ENTERPRISE | 4.38 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHERKHANCHAK W/S SCH, BHAGAWANPUR-I BLOCK UNDER MEDINIPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000155/2022-2023 | 435/CDD | 23/05/2022 | 22/06/2022 | MENAKA ENTERPRISE | 14.69 | 0 | 0 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well No I of Zone II under Sherkhan Chack water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001134/2022-2023 | 2115/W/MMD | 28/11/2022 | 28/03/2023 | BHABANI PRASAD MANNA | 11.56 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for the office of The Assistant Engineer, S&WSD,CDD, PHE Dte. |  |  | ORD/000341/2022-2023 | 232/S&WSD | 20/12/2022 | 27/12/2022 | NAGENDRA PATRA | 0.86 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SERKHAN CHAK W/S SCHEME, ZONE-I, TW-III, KHEJURI-II BLOCK, UNDER PURBA MIDNAPORE DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000375/2022-2023 | 1381/CDD | 24/11/2022 | 24/12/2022 | MENAKA ENTERPRISE | 22.11 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Assistant Engineer, S&WSD, CDD, PHE Dte. |  |  | ORD/000018/2023-2024 | 74/S&WSD | 30/06/2023 | 30/07/2023 | NAGENDRA PATRA | 0.15 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 300 mtrs. Depth) by utilising Departmental machineries for Serkhanchak W/S Scheme (TW-III), Khejuri-II block under Purba Midnapore District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000453/2022-2023 | 1346/CDD | 24/11/2022 | 24/12/2022 | MENAKA ENTERPRISE | 22.2 | 0 | 0 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 1198/TD | 06/09/2022 | 06/09/2022 | Resource Division | 15.39 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 1210/TD | 06/09/2022 | 06/09/2022 | Resource Division | 15.91 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 300 Mtrs. Depth) by utilising Departmental Machineries for Serkhan Chawk W/S Scheme (TW-¦V) , Khejuri-ll Block under Purba Midnapore Dlstrict, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000517/2022-2023 | 1536/CDD | 08/12/2022 | 07/01/2023 | MENAKA ENTERPRISE | 22.23 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 250cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Sherkhanchak Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000208/2022-2023 | 816/TD | 12/07/2022 | 12/04/2025 | SRIMANTA KUMAR MAITY | 406.75 | 0 | 0 | 70
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001476/2022-2023 | 214/W/MMD | 10/02/2023 | 30/04/2024 | EMCON | 11.83 | 0 | 0 | 85
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Name of Work: i) Laying Rising main and other allied works Augmentation of Sherkhanchak Zone-II W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000871/2022-2023 | 3222/TD | 14/03/2023 | 23/12/2024 | SRIMANTA KUMAR MAITY | 7.4 | 0 | 0 | 100
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11469 | Augmentation | Laying of Left-Out portion uPVC Pipe line, Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site under Sherkhanchak Zone-II Water Supply Scheme (Augmentation) in Khejuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001218/2023-2024 | 982/TD | 13/03/2024 | 06/02/2025 | BIPLAB GUHA | 86.79 | 0 | 0 | 60
Total | [13 empty] | 650.96 | 0 | 0