## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11470 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Natshal Lakshya Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000016/2022-2023 | 50/TD | 05/04/2022 | 25/04/2022 | RADIANT | 5.44 | 5.36 | 98.36 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11470 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000334/2022-2023 | 1249/TD | 12/09/2022 | 22/10/2022 | SIMPLEX DRILLING COMPANY | 83.68 | 19.47 | 23.27 | 75
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11470 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 1375/TD | 23/09/2022 | 23/09/2022 | Resource Division | 52.31 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11470 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001472/2022-2023 | 210/W/MMD | 10/02/2023 | 09/08/2023 | M/S S.G. ENTERPRISE | 27.26 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11470 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000747/2022-2023 | 2594/TD | 30/01/2023 | 29/07/2023 | RAJ KUMAR SINGHA | 986.55 | 507.95 | 51.49 | 65
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11470 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 30/08/2023 | S.S.GHORAI | 0.9 | 0 | 0 | 53
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11470 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000235/2022-2023 | 2617/TD | 02/02/2023 | 02/02/2023 | Resource Division | 139.61 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11470 | Augmentation | Fuel charges for hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission program. For the month of JUNE"2023 Vehicle no-WB31-9339 W/O NO-101/HESD DT-27/02/2023 SM/11470 |  |  | BILL/06213/2025-2026 |  | 12/03/2026 | 12/03/2026 | S.S.GHORAI | 0.14 | 0 | 0 | 0
Total | [13 empty] | 1295.9 | 532.78 | 41.11