## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000464/2022-2023 | 1876/TD | 22/11/2022 | 22/12/2022 | PRASANTA MONDAL | 4.13 | 4 | 96.97 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rt Tube Well site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000493/2022-2023 | 1879/TD | 22/11/2022 | 21/01/2023 | DIPANKAR MALAKAR | 5.11 | 5.09 | 99.71 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Construction of boundary wall in 3rd tubewell site of Natshal Lakshya Zone II under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Assistant Engineer | Junior Engineer | ORD/000396/2023-2024 | 1080/TD | 08/06/2023 | 08/07/2023 | M/S SOURAV MAHAPATRA | 5.91 | 5.27 | 89.13 | 100
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Electric Quotation for NATSHALLAKHYA Water Supply Scheme Z-II, T/W-III (Ref. ID-204048971) |  |  | BILL/01635/2023-2024 | BP-2023-24-140 | 27/07/2023 | 27/07/2023 | WBSEDCL | 4.26 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000747/2022-2023 | 2594/TD | 30/01/2023 | 29/07/2023 | RAJ KUMAR SINGHA | 986.55 | 183.73 | 18.62 | 65
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001755/2022-2023 | 634/W/MMD | 20/03/2023 | 16/09/2023 | JOYSHREE CONCERN | 13.56 | 13.46 | 99.24 | 90
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Natshal Lakshya W/S Scheme (Z-II, T/W-II), Mahisadal Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000123/2023-2024 | 876/CDD | 11/07/2023 | 31/07/2024 | MENAKA ENTERPRISE | 21.16 | 19.11 | 90.32 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte.(for Tabakhali PWSS, Dakshinchak Zone-1 PWSS, Dakshinchak Zone-II PWSS, Natshal lakshya Zone-II PWSS) (Phase-V) | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 766/HSD, | 27/02/2024 | 05/03/2024 | SNEHASIS BERA | 0.83 | 0.83 | 99.62 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11471 | Augmentation | Canal crossing , laying Rising main, Construction of boundary wall of Head work site & 2nd TW site & Drum Sheet walling of Natshal Lakshya (Zone-II) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000590/2023-2024 | 2207/TD | 01/09/2023 | 15/01/2025 | RAJ KUMAR SINGHA | 91.71 | 67.66 | 73.77 | 30
Total | [13 empty] | 1133.22 | 299.15 | 26.4