## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rt Tube Well site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  | Junior Engineer | ORD/000492/2022-2023 | 1878/TD | 22/11/2022 | 21/01/2023 | M/S SOURAV MAHAPATRA | 5.03 | 4.99 | 99.02 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000491/2022-2023 | 1877/TD | 22/11/2022 | 22/12/2022 | MODERN CONSTRUCTION | 4.06 | 4.01 | 98.97 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 1013/TD | 08/08/2022 | 08/08/2022 | Resource Division | 106.84 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Electric quotation for Natshallakhya PWSS Tube Well- III, Zone-I in connection Mukundapur CCC (2004197468) |  |  | BILL/00160/2022-2023 | BP-2022-23-128 | 13/03/2023 | 13/03/2023 | WBSEDCL | 0.59 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Supply and delivery of CIDF sluice valve,construction of sluice valve chamber ,Canal crossing & pilling work of ground water based Natshal Lakshya (Zone-I) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(for Part-B) | Assistant Engineer | Junior Engineer | ORD/000338/2023-2024 | 803/TD | 30/05/2023 | 29/06/2023 | BARH CONSTRUCTION | 25.52 | 12.05 | 47.21 | 40
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 2nd Tubewell Site of Natshal Lakshya Zone - I W/S Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 5th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 4th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000543/2023-2024 | 1905/TD | 10/08/2023 | 19/09/2023 | AQUATECH ENGINEER | 58.34 | 20.45 | 35.05 | 45
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 4th & 5th Tube well of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Development Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer |  | ORD/000196/2024-2025 | 2321/TD | 23/07/2024 | 01/09/2024 | MANNA COMPUTER | 39.77 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001473/2022-2023 | 211/W/MMD | 10/02/2023 | 09/08/2023 | S.B.ENTERPRISE | 13.65 | 13.41 | 98.23 | 75
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Construction of boundary wall in OHR site of Natshal Lakshya (Zone-I) Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-155mtr) | Assistant Engineer | Junior Engineer | ORD/000610/2023-2024 | 2254/TD | 05/09/2023 | 20/10/2023 | PRAMANIK AND ROY CONSTRUCTION | 13.18 | 11 | 83.42 | 100
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Replacement of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Tube Well-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur Districtunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002727/2023-2024 | 1072/W/MMD | 14/03/2024 | 10/09/2024 | ECO ENTERPRISE | 10.85 | 10.61 | 97.74 | 90
11 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Natshal Lakshya W/S Scheme (Z-I, T/W-I) , Mahisadal Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000214/2023-2024 | 1391/CDD | 19/09/2023 | 10/04/2024 | DEV AND COMPANY | 21.16 | 19.89 | 93.98 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (3772 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000903/2022-2023 | 3459/TD | 27/03/2023 | 28/12/2025 | SANKHA ENTERPRISE | 609.47 | 0 | 0 | 25
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Construction of boundary wall in 3rd tubewell site of Natshal Lakshya (Zone-I) W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Assistant Engineer | Junior Engineer | ORD/000339/2023-2024 | 804/TD | 30/05/2023 | 20/03/2025 | TAPAN BERA | 5.92 | 0 | 0 | 60
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Construction of (5.40 Mtr. X 3.60 Mtr.) Chlorine Room including Plinth Protection at Natshal Lakshya Store within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000542/2024-2025 | 204/TD | 15/01/2025 | 24/06/2025 | BHOWMIK & SONS | 6.18 | 0 | 0 | 80
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11473 | Augmentation | Construction of 2 nos (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 4th Tube Well site & 5th Tube well site, Laying of Rising main with interconnection, and Supplying of D.I. Specials for Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000135/2024-2025 | 1924/TD | 07/06/2024 | 22/04/2025 | TAPAN BERA | 22.25 | 0 | 0 | 50
Total | [13 empty] | 942.81 | 96.4 | 10.22