## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Laying of distribution pipe line to accommodate FHTC (5686 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Anantapur Zone-II Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000481/2022-2023 | 1885/TD | 24/11/2022 | 28/09/2025 | TAPAS SANTRA | 609.95 | 450.15 | 73.8 | 75
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anantapur (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000463/2021-2022 | 1740/TD | 03/02/2022 | 23/02/2022 | RADIANT | 3.89 | 3.86 | 99.21 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 1018/TD | 08/08/2022 | 08/08/2022 | Resource Division | 88.34 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 1207/TD | 06/09/2022 | 06/09/2022 | Resource Division | 2.44 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 230 mtrs. depth) by utilising Departmental machineries for Anantapur W/S Scheme (Z-II, TW-III) Tamluk block under purba medinipur district, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000427/2022-2023 | 2116/CDD | 02/03/2023 | 01/04/2023 | MENAKA ENTERPRISE | 17.75 | 16.11 | 90.74 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Anantapur Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000398/2023-2024 | 1082/TD | 08/06/2023 | 23/07/2023 | TARUN KHATUA | 5.1 | 5.1 | 99.97 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001740/2022-2023 | 641/W/MMD | 20/03/2023 | 16/09/2023 | M/S. JIT ENTERPRISE | 13.59 | 9.63 | 70.86 | 35
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Laying of 200 /250/300mm dia DI(K-9) for Rising main line from T/W-1 , T/W-2 ,T/W-3 and interconnection betn. T/W-1 to OHR including supply of DI specials , Construction of approach road at 3rd tube well site under Anantapur Zone- II PWSS with in Tamluk Dev. Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000579/2023-2024 | 2201/TD | 01/09/2023 | 21/09/2023 | TARUN KHATUA | 8.66 | 8.49 | 98.1 | 80
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work Site of Anantapur Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000600/2023-2024 | 2213/TD | 01/09/2023 | 11/10/2023 | TARUN KHATUA | 5.14 | 5.12 | 99.7 | 100
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Electric Quotation for ANANTAPUR, Water Supply Scheme ,Zone-I, T/W-III, (Ref. ID-204060666) |  |  | BILL/01816/2023-2024 | BP-2023-24-189 | 14/08/2023 | 14/08/2023 | WBSEDCL | 6.18 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Electric Quotation for ANANTAPUR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048948) |  |  | BILL/01775/2023-2024 | BP-2023-24-188 | 11/08/2023 | 11/08/2023 | WBSEDCL | 9.99 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Repairing & renovation of Switch Room cum Chlorine Room at 2nd Tube Well site and Boundary Wall at Head Work site of Anantapur Zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engiener | ORD/000304/2024-2025 | 2904/TD | 10/09/2024 | 14/12/2025 | TAPAS SANTRA | 27.24 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Additional Laying Distribution System of 200 mm dia upvc pipe line, Drumpsheet Pilling and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 300 mm dia(sec 19-23) and 180 mm dia(sec-22-57) of pipe line of Ananantapur Zone-II Water Supply Scheme of Tamluk Sub-Division under Tamluk Division P.H.E. Dte. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000308/2024-2025 | 3138/TD | 26/09/2024 | 24/04/2025 | TAPAS SANTRA | 53.77 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11549 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000223/2023-2024 | 1122/TD | 18/03/2024 | 18/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
Total | [13 empty] | 852.24 | 498.46 | 58.49