## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Solat Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000459/2021-2022 | 1723/TD | 01/02/2022 | 21/02/2022 | RADIANT | 3.65 | 3.58 | 98.19 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001517/2022-2023 | 361/W/MMD | 09/03/2023 | 05/09/2023 | AMIT DAS | 13.56 | 12.85 | 94.73 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 01/11/2022 | B. K. ENTERPRISE | 72.46 | 19.05 | 26.29 | 63
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase -1) Name of Work site :- 1) Asadtalia PWSS, 2) Rangibasan PWSS, 3) Kapaseria PWSS, 4) Rajarampur PWSS, 5) Begunberia PWSS, 6) Dhenkua PWSS, 7) Solat PWSS & 8) Gopalpur PWSS. | Assistant Engineer | Junior Engineer | ORD/000438/2022-2023 | 721/HSD | 28/10/2022 | 31/10/2022 | TAPAN BERA | 0.93 | 0.93 | 100 | 100
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 1019/TD | 08/08/2022 | 08/08/2022 | Resource Division | 12.18 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 1201/TD | 06/09/2022 | 06/09/2022 | Resource Division | 16.27 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Additional drilling works & other materials at site for construction of Tube Well at Solat W/S Scheme, Haldia Block, Purba MedinipurDist. under CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000021/2024-2025 | 146/CMSD-II | 22/07/2024 | 01/08/2024 | PADMA ENGINEERING & CO. | 0.99 | 0.79 | 79.2 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Providing Tube Well materials Conforming to IS: 12818:2010 at site for construction of Tube Well at Solat PWSS, Purba Medinipur district under CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000020/2024-2025 | 145/CMSD-II | 22/07/2024 | 29/07/2024 | PADMA ENGINEERING & CO. | 0.97 | 0.97 | 100 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Quotation bill for new service connection at TW-III of solat w/s scheme under Haldia block in the Dist. of purba medinipur under MMD,PHE Dte. Name of C.C.C.-Brajalalchak Application no.-2004898781 Reference ID-204397568 Contract Demand-12074watt Quotation Date-12/09/2024 Quotation Due Date-12/09/2025 |  |  | BILL/00955/2024-2025 | BP-2024-25-632 | 26/11/2024 | 26/11/2024 | WBSEDCL | 10.59 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Augmentation of ground water based Solat Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000298/2022-2023 | 1113/TD | 29/08/2022 | 30/05/2026 | ARUP KUMAR DEY | 454.08 | 289.11 | 63.67 | 83
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipment¿s at TW II for Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000074/2023-2024 | 1243/W/MMD | 28/04/2023 | 31/01/2025 | M/S EMMESS | 13.59 | 6.63 | 48.79 | 60
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Additional Laying of Distribution pipeline,Drum Sheet Walling,G.I. Casing & Laying Rising Main of Solat Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000364/2023-2024 | 932/TD | 01/06/2023 | 02/09/2025 | SANKHA ENTERPRISE | 68.51 | 0 | 0 | 40
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District. | SM/11552 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Solat Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000473/2023-2024 | 1499/TD | 17/07/2023 | 18/12/2024 | ELECTIVA ENTERPRISE | 5.1 | 0 | 0 | 100
Total | [13 empty] | 672.88 | 333.9 | 49.62