## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shilaberia-Janka Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2021-2022 | 1647/TD | 19/01/2022 | 08/02/2022 | ROY CHOWDHURY ASSOCIATES | 4.96 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 1659/TD | 03/11/2022 | 03/11/2022 | Resource Division | 186.64 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 1376/TD | 23/09/2022 | 23/09/2022 | Resource Division | 13.06 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-I, Zone-II (Ref. ID-204049345) |  |  | BILL/01676/2023-2024 | BP-2023-24-156 | 04/08/2023 | 04/08/2023 | WBSEDCL | 0.97 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA JANKA, Water Supply Scheme T/W-IV, Zone-I (Ref. ID-204049555) |  |  | BILL/01679/2023-2024 | BP-2023-24-159 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.8 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-II, Zone-II (Ref. ID-204049556) |  |  | BILL/01677/2023-2024 | BP-2023-24-157 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.4 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-IV, Zone-II (Ref. ID-204049361) |  |  | BILL/01675/2023-2024 | BP-2023-24-155 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.97 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-III, Zone-II (Ref. ID-204049047) |  |  | BILL/01678/2023-2024 | BP-2023-24-158 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.3 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000437/2022-2023 | 1650/TD | 02/11/2022 | 01/05/2023 | TARUN KOLEY | 942.75 | 0 | 0 | 85
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II (Phase-2) | SM/11554 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II,under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000082/2023-2024 | 1274/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 50.28 | 0 | 0 | 70
Total | [13 empty] | 1209.13 | 0 | 0