## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11612 | Augmentation | additional compressor development of the newly construction tube well at argoal w/s scheme 2nd tw site, block-pataspur -ii under CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000191/2020-2021 | 63/CMSD-I | 18/03/2021 | 21/03/2021 | ASHUTOSH DAS & CO | 0.49 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11612 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 27/09/2022 | AQUATECH ENGINEERS | 55.36 | 14.62 | 26.4 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11612 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. Block ¿ Potashpur II within the Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001738/2022-2023 | 640/W/MMD | 20/03/2023 | 16/09/2023 | PURUSHOTTAM ENTERPRISE | 13.57 | 13.27 | 97.79 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11612 | Augmentation | Laying Rising Main DI(K-9) pipe line with interconnection, Construction of 3.60 mtr. X 3.00 mtr. Size Switch Room cum Chlorine Room & Boundary Wall at 3rd Boosting TW site (Mouza-Jabda, J.L No-225, Plot No-887) of Argoal PWSS in Patashpur-II within Contai Sub-Division of Tamluk Division,PHE Dte.(Length-50.00 mtr.) (for Low Land) | Assistant Engineer | Junior Engineer | ORD/000487/2023-2024 | 1521/TD | 18/07/2023 | 17/08/2023 | SK. SARFARAJ | 33.57 | 9.68 | 28.83 | 90
5 | PURBA MEDINIPUR |  | Tamluk Division | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11612 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 357/TD | 26/04/2023 | 26/04/2023 | Resource Division | 17.67 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11612 | Augmentation | Electric quotation bill for WBSEDCL at TW III of Argoal WS Scheme (Ref. ID - 203932077) |  |  | BILL/00060/2023-2024 | BP-2023-24-7 | 18/04/2023 | 18/04/2023 | WBSEDCL | 0.74 | 0 | 0 | 0
Total | [13 empty] | 121.39 | 37.56 | 30.95