## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Moyna Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000859/2021-2022 | 1470/TD | 03/01/2022 | 23/01/2022 | APEX ENGINEERING | 4.08 | 3.93 | 96.33 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Providing Drilling crew and other allied works for construction of Tube Well (300mm x 200mmx 230 Mtrs. Depth) by utilising Departmental Mechineries for Moyna W/S Scheme (Z-I,T/W-I)block under Purba Medinipur District CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000028/2023-2024 | 537/CDD | 02/06/2023 | 02/07/2023 | MENAKA ENTERPRISE | 17.76 | 16.24 | 91.48 | 100
3 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 230 Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-I, T/W-I), Moyna Block under Purba Medinipur District , Central Drilling Division PHE Dte. | Driller In Charge | Junior Engineer | ORD/000033/2023-2024 | 538/CDD | 02/06/2023 | 02/07/2023 | MENAKA ENTERPRISE | 17.76 | 16.24 | 91.48 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 1209/TD | 06/09/2022 | 06/09/2022 | Resource Division | 131.09 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 1205/TD | 06/09/2022 | 06/09/2022 | Resource Division | 7.03 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1922/TD | 14/08/2023 | 14/08/2023 | Resource Division | 9.63 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH line at Moyna Zone-I Water Supply Scheme |  |  | BILL/01475/2023-2024 | BP-2023-24-663 | 15/12/2023 | 15/12/2023 | WBSEDCL | 3.97 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Continuation work order for Hiring of one no Diesel Motor cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, (Vehicle No. WB-29B-2278) on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte under Tamluk Division for the period from 01.01.2024 to 31.03.2024. | Assistant Engineer | Junior Engineer | ORD/001226/2023-2024 | 1756/TSD | 29/12/2023 | 17/02/2024 | DEBNATH MAITY | 0.24 | 1.11 | 466.61 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Laying of left out pipe line by 90 mm OD UPVC pipes with allied works of Moyna Zone-I & its adjoining mouzas Water Supply Scheme within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000108/2024-2025 | 1902/TD | 07/06/2024 | 02/07/2024 | GHOSH ENTERPRISE | 70.24 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th. T/W Site. of Moyna Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000597/2023-2024 | 2211/TD | 01/09/2023 | 11/10/2023 | PRASANTA MONDAL | 5.1 | 4.9 | 95.95 | 10
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Moyna Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000598/2023-2024 | 2212/TD | 01/09/2023 | 11/10/2023 | PRASANTA MONDAL | 5.1 | 5.01 | 98.1 | 70
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 1099/TD | 19/03/2024 | 19/03/2024 | Resource Division | 0.19 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Electric Quotation for MOYNA Water Supply Scheme T/W-IV, Zone-I, (Ref. ID-204136064) |  |  | BILL/03186/2023-2024 | BP-2023-24-437 | 18/12/2023 | 18/12/2023 | WBSEDCL | 4.91 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Electric Quotation for MOYNA Water Supply Scheme T/W-III, Zone-I, (Ref. ID-204143546) |  |  | BILL/03134/2023-2024 | BP-2023-24-408 | 09/12/2023 | 09/12/2023 | WBSEDCL | 4.7 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Laying of distribution pipe line to accommodate FHTC (4679 nos) with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Moyna Zone-I Water Supply Scheme within Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000442/2022-2023 | 1652/TD | 02/11/2022 | 23/04/2025 | ARABINDA GHOSH | 612.74 | 336.18 | 54.86 | 85
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Laying of 300/250/200/150 mm dia DI (K9) rising main in between OHR to T/W-I, T/W-2, T/W-3 and T/W-4 including canel crossing and dram Sheet Walling and DI specials of Moyna Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000653/2023-2024 | 2618/TD | 11/10/2023 | 04/12/2024 | KRISHNENDU SEKHAR DAS | 24.68 | 3.4 | 13.79 | 100
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Repairing & Renovation of Construction of Pump house ,Boundary wall & allied works at 1st Tube well 2nd tube well site of Moyna Zone-I Water Supply Scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000430/2024-2025 | 3547/TD | 18/11/2024 | 18/12/2024 | SANDIP MAITI | 3.06 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 12 (Twelve) Months. | Assistant Engineer | Junior Engineer | ORD/001259/2023-2024 | 1468/TSD | 31/10/2023 | 26/06/2024 | TAPAS SANTRA | 1.14 | 3.97 | 350.14 | 0
19 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Moyna (Zone-I) PWSS | SM/11614 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Augmentation of Moyna (Zone-I) PWSS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001752/2022-2023 | 645/W/MMD | 20/03/2023 | 30/08/2024 | SOUMEN ELECTRIC | 27.17 | 26.82 | 98.73 | 60
Total | [13 empty] | 950.58 | 417.81 | 43.95