## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 01/11/2022 | B. K. ENTERPRISE | 72.46 | 0 | 0 | 63
2 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 1660/TD | 03/11/2022 | 03/11/2022 | Resource Division | 143.41 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 610/TD | 17/05/2023 | 17/05/2023 | Resource Division | 23.76 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Electric Quotation for CONTAI S.A.Rej. Water Supply Scheme T/W-I, Part-A, Zone-I (Ref. ID-204050258) |  |  | BILL/01686/2023-2024 | BP-2023-24-164 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.34 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Electric Quotation for CONTAI S.A.Rej. Water Supply Scheme T/W-II, Part-A, Zone-I (Ref. ID-204050190) |  |  | BILL/01687/2023-2024 | BP-2023-24-163 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.48 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A),under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000158/2023-2024 | 1393/W/MMD | 01/06/2023 | 28/11/2023 | P.K.ENGINEERING | 27.18 | 0 | 0 | 30
7 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Payment of wayleave facility charges (SER-KGP-2024-WL-47) |  |  | BILL/00135/2024-2025 | BP-2024-25-78 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.38 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Payment of wayleave facility(SER-KGP-2024-WL-48) |  |  | BILL/00136/2024-2025 | BP-2024-25-79 | 29/04/2024 | 29/04/2024 | FA & CAO, S.E. RAILWAY, GRC. | 5.25 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Contai Saline Area Zone-I (Phase - A) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-I) | Assistant Engineer | Junior Engineer | ORD/000633/2022-2023 | 2314/TD | 05/01/2023 | 26/09/2025 | DAS CONSTRUCTION | 456.2 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A). | SM/11615 | Augmentation | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Contai Saline Area Zone-I ( Phase - A) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-II) | Assistant Engineer | Junior Engineer | ORD/000670/2022-2023 | 2311/TD | 05/01/2023 | 14/09/2025 | DAS CONSTRUCTION | 230.47 | 0 | 0 | 0
Total | [13 empty] | 968.94 | 0 | 0