## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Instalation of display Board at different work site of Augmentation of Shilaberia Zone-I-1 no, Shilaberia Zone-II-1 no, Durmuth-1 no, Amarshikasba Zone-I-1 no, Amarshikasba Zone-II-1 no, Golaranij-1 no & Mukutshila Zone-I-1 no PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000509/2022-2023 | 809 / CSD | 21/10/2022 | 05/11/2022 | THE GODFATHER TRADING COMPANY | 0.81 | 0.81 | 99.85 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000203/2023-2024 | 397/TD | 27/04/2023 | 17/05/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.02 | 2.02 | 100 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000202/2023-2024 | 396/TD | 27/04/2023 | 17/05/2023 | MA SARADA ENTERPRISE | 8.14 | 8.14 | 100 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 1657/TD | 03/11/2022 | 03/11/2022 | Resource Division | 106.02 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-III, Zone-I (Ref. ID-204049557) |  |  | BILL/01674/2023-2024 | BP-2023-24-154 | 04/08/2023 | 04/08/2023 | WBSEDCL | 2.55 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001911/2022-2023 | 812/W/MMD | 24/03/2023 | 07/03/2025 | DEBJYOTI BASU | 54.33 | 28.88 | 53.16 | 25
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 1653/TD | 02/11/2022 | 30/08/2025 | TAPAS SANTRA | 997.19 | 251.77 | 25.25 | 70
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Repair and renovation of of Boundary Wall (as per Departmental Design & Drawing) at OHR site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Length-78.00 mtr.) | Assistant Engineer |  | ORD/000199/2024-2025 | 2324/TD | 23/07/2024 | 01/09/2024 | S.D. CONSTRUCTION | 10.42 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Shillaberia Jhanka Zone-I PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. ii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 4th Tube Well Site for Shillaberia Jhanka Zone-I PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000825/2022-2023 | 3144/TD | 09/03/2023 | 18/04/2023 | B. K. ENTERPRISE | 35.19 | 33.45 | 95.06 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Name of Work: i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Shillaberia Jhanka Zone-I & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iv) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-I & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) v) Rising main and other allied works Augmentation of Shillaberia Jhanka Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000862/2022-2023 | 3218/TD | 14/03/2023 | 04/07/2025 | BARH CONSTRUCTION | 46.11 | 7.76 | 16.82 | 80
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Laying of left out pipe line by HDPE pipes with allied works, Repair and renovation of Pump House, Toilet and others allied works at OHR's site under Shillaberia Zone-I Water Supply scheme (Augmentation) in Khjuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 2696/TD | 22/08/2024 | 19/04/2025 | TAPAS SANTRA | 57.33 | 0 | 0 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Land Development at 3rd Tube Well site of Shillaberia Jhanka Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001285/2023-2024 | 369/CSD | 23/02/2024 | 09/03/2024 | ABHIJIT BERA | 0.51 | 0 | 0 | 100
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Land Development at 4th Tube Well site of Shillaberia Jhanka Zone-I PWSS within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000416/2024-2025 | 2002/CSD | 06/08/2024 | 21/08/2024 | GIRI CONSTRUCTION | 1.8 | 0 | 0 | 100
14 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | ADDITIONAL QUOTATION FOR SHILSBERIA, ZONE-I W/S PH-IV UNDER JJM UNDER MIDNAPORE MECHANICAL DIVISION,PHE DTE. WBSEDCL CUSTOMER CARE OFFICE: KHEJURI C.C.C. BLOCK- KHEJURI-II MEMO NO: KJR/QI/392 Dated:18.12.2025 Reference ID: 860358767 DT.18.12.2025 Application ID:100000155107 DT.18.12.2025 |  |  | BILL/04138/2025-2026 |  | 23/12/2025 | 23/12/2025 | WBSEDCL | 3.49 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) | SM/11617 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shilaberia Janka Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. |  |  | ORD/000011/2022-2023 | 45/TD | 05/04/2022 | 25/04/2022 | INDRANIL DUTTA & ASSOCIATES | 5.26 | 0 | 0 | 100
Total | [13 empty] | 1331.17 | 332.83 | 25