## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) | SM/11618 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 1372/TD | 23/09/2022 | 23/09/2022 | Resource Division | 38.75 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) | SM/11618 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 1658/TD | 03/11/2022 | 03/11/2022 | Resource Division | 180.08 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-2) | SM/11618 | Augmentation | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 1653/TD | 02/11/2022 | 30/08/2025 | TAPAS SANTRA | 997.19 | 0 | 0 | 70
Total | [13 empty] | 1216.02 | 0 | 0