## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Laying of distribution pipe line to accommodate FHTC (3870 nos) with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Moyna Zone-II Water Supply Scheme within Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000443/2022-2023 | 1651/TD | 02/11/2022 | 17/10/2025 | ARABINDA GHOSH | 571.76 | 481.85 | 84.27 | 80
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Moyna Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000860/2021-2022 | 1469/TD | 03/01/2022 | 23/01/2022 | APEX ENGINEERING | 4.37 | 3.98 | 91.16 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 1204/TD | 06/09/2022 | 06/09/2022 | Resource Division | 7.03 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 1206/TD | 06/09/2022 | 06/09/2022 | Resource Division | 109.03 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Pump House , Boundary Wall, Rising Main, Dramsheet Pilling for Augmentation of Moyna Zone-II Water Supply Scheme under Moyna Development Block within Tamluk Sub-Division under Tamluk Division, PHE Dte.in the district Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000465/2023-2024 | 1445/TD | 13/07/2023 | 10/10/2025 | GHOSH ENTERPRISE | 89.23 | 36.26 | 40.64 | 81
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Moyna (Zone-II) PWSS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001715/2022-2023 | 630/W/MMD | 20/03/2023 | 31/08/2024 | ALPHA ENTERPRISE | 37.86 | 35.46 | 93.65 | 70
7 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 230Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-Ii, T/W-III) Moyna Block under Purba Medinipur District CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000038/2023-2024 | 539/CDD | 02/06/2023 | 02/07/2023 | MENAKA ENTERPRISE | 17.76 | 15.47 | 87.11 | 100
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 230Mtrs. Depth) by utilising Departmental machineries for Moyna W/S Scheme (Z-Ii, T/W-IV) Moyna Block under Purba Medinipur District CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000037/2023-2024 | 540/CDD | 02/06/2023 | 02/07/2023 | MENAKA ENTERPRISE | 17.76 | 16.14 | 90.93 | 100
9 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Moyna W/S Scheme (Z-II,T/W-V ) , Moyna Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000129/2023-2024 | 541/CDD | 02/06/2023 | 02/07/2023 | MENAKA ENTERPRISE | 17.76 | 15.8 | 89.01 | 100
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Moyna W/S scheme T/W-III, Z-II Ref.-204143545 |  |  | BILL/03164/2023-2024 | BP-2023-24-436 | 18/12/2023 | 18/12/2023 | WBSEDCL | 2.74 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Electric Quotation for MOYNA Water Supply Scheme T/W-I,Zone-II, (Ref. ID-204143547) |  |  | BILL/03133/2023-2024 | BP-2023-24-409 | 09/12/2023 | 09/12/2023 | WBSEDCL | 5.37 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Proposed Retaining Wall cun Guard wall and Approach Road beside pond at 3rd Tube well for Augmentation of Moyna Zone-II PWSS under Moyna Development Block under Tamluk Sub- Division in Tamluk Divisionin the District of Purba Medinipur. |  |  | ORD/000239/2024-2025 | 2678/TD | 22/08/2024 | 16/09/2024 | GHOSH ENTERPRISE | 6.98 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Moyna W/S scheme PH.-II, Zone-II Application No.-2004557342 Ref.-204187844 |  |  | BILL/03367/2023-2024 | BP-2023-24-577 | 18/01/2024 | 18/01/2024 | WBSEDCL | 8.84 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | Bill for damage of Moyna Bridge approach road at 1.90 Km. Due to laying of water pipe line for Moyna Zone-II PWSS |  |  | BILL/00992/2024-2025 | BP-2024-25-496 | 01/10/2024 | 01/10/2024 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.41 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Moyna (Zone-II) PWSS | SM/11639 | Augmentation | PENDING PAYMENTS FROM PHED FOR ROAD RESTORATION WORK OF DIFFERENT ROAD UNDER TAMLUK HIGHWAY DIVISION P.W.(ROADS) DIRECTORATE Memo No. 340 Dated 21.02.2025 of the Executive Engineer, Tamluk Highway Division |  |  | BILL/00709/2025-2026 |  | 20/08/2025 | 20/08/2025 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.38 | 0 | 0 | 0
Total | [13 empty] | 897.26 | 604.96 | 67.42