## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Operation and Maintenance of laboratory activity for Physical, Chemical and Bacteriological testing of water at Contai Sub Divisional Laboratory of Public Health Engineer Dte. at Contai under Tamluk Division for the period from 01/01/2021 to 30/09/2021.( 9 months) | Assistant Engineer |  | ORD/000265/2020-2021 | 2581/TD | 30/12/2020 | 30/09/2021 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.54 | 4.54 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Engagement of 3 Nos. Laboratory Personnel (One No. Chemist / Bacteriologist, One no. Laboratory Assistant & One no. Sampling Assistant) for regular analysis, testing, and monitoring of water sample and other allied minor mtc. Work of Digha Sub-Divisional Laboratory under Digha Sub-Division of Tamluk Division, PHE Dte. for the period from 01/04/2020 to 31/03/2021 i.e. 12 (twelve) months. |  |  | ORD/000026/2019-2020 | 2497/TD | 31/03/2020 | 31/03/2020 | ARUNALOY SCIENTIFIC HOUSE | 4.81 | 0.56 | 11.55 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Operation and Maintenance of laboratory activity for Physical, Chemical and Bacteriological testing of water at Contai Sub Divisional Laboratory of Public Health Engineer Dte. at Contai under Tamluk Division for the period from 01/10/2021 to 30/06/2022.( 9 months) | Assistant Engineer |  | ORD/000473/2021-2022 | 806-A/TD | 29/09/2021 | 29/06/2022 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.36 | 4.36 | 99.99 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Providing services for operation of 07 (Seven) nos. PHED managed Sub-District laboratories under Tamluk Division, PHE Dte. by engaging one Chemist/Bacteriologist and one Laboratory Assistant for each laboratory capable to analyze chemical, bacteriological and physical parameter of water with sophisticated and prescribed electronic equipment including sending data through smart phone, preparation of test result, cleaning of instruments, glassware furniture etc. and other laboratory related works as per guidelines of WSSO, PHE Department for 12 (Twelve) Months. | Assistant Engineer |  | ORD/000658/2021-2022 | 2354/TD | 31/03/2022 | 31/03/2023 | UTSAV AGENCY | 24.85 | 24.18 | 97.28 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Engagement of 03 nos. Sampling Assistants and 06 nos. Laboratory Attendants for different PHED Managed Water Testing Laboratories under Tamluk Division, PHE Dte. For the period 06 (Six) Months from 01.01.2023 to 30.06.2023 | Assistant Engineer |  | ORD/000601/2022-2023 | 2257/TD | 30/12/2022 | 30/06/2023 | UTSAV AGENCY | 7.99 | 6.74 | 84.36 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Continuation Work Order for Providing services for operation of 07 (Seven) nos. PHED managed Sub-District laboratories under Tamluk Division, PHE Dte. by engaging one Chemist/Bacteriologist and one Laboratory Assistant for each laboratory capable to analyze chemical, bacteriological and physical parameter of water with sophisticated and prescribed electronic equipment including sending data through smart phone, preparation of test result, cleaning of instruments, glassware furniture etc. and other laboratory related works as per guidelines of WSSO, PHE Department for 02 (Two) Months. (From 01.04.2023 to 31.05.2023) | Assistant Engineer |  | ORD/000962/2022-2023 | 3583/TD | 30/03/2023 | 30/05/2023 | UTSAV AGENCY | 4.02 | 3.9 | 96.97 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Chemicals and other required items related to smooth functioning of NABL Recognition (16 nos.) Labs under Tamluk Division PHE Dte. | Assistant Engineer |  | ORD/000476/2023-2024 | 1534/TD | 18/07/2023 | 17/08/2023 | UTSAV AGENCY | 6.18 | 6.18 | 100 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00265/2023-2024 | BP-2023-24-140 | 19/06/2023 | 19/06/2023 | ABHYUDAYA HALDIA | 1.35 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Bill for contingency expenses of Vivekananda Yuba Parishad Water testing laboratory for the period of April-2022 to March-2023 |  |  | BILL/00455/2023-2024 | BP-2023-24-263 | 17/08/2023 | 17/08/2023 | VIVEKANANDA YUBA PARISHADISP | 0.75 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Bill for contingency expenses of Bhagwanpur-II Vivekananda Kalyan Parishad Water testing laboratory for the period of April-2022 to March-2023 |  |  | BILL/00453/2023-2024 | BP-2023-24-261 | 17/08/2023 | 17/08/2023 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 0.75 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. |  |  | BILL/00039/2023-2024 | BP-2023-24-33 | 29/04/2023 | 29/04/2023 | GRAMMANGAL WATER TESTING LAB | 1.32 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00263/2023-2024 | BP-2023-24-138 | 19/06/2023 | 19/06/2023 | GRAMMANGAL WATER TESTING LAB | 1.35 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00728/2023-2024 | BP-2023-24-411 | 26/09/2023 | 26/09/2023 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.35 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00727/2023-2024 | BP-2023-24-410 | 26/09/2023 | 26/09/2023 | ABHYUDAYA HALDIA | 1.35 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00259/2023-2024 | BP-2023-24-134 | 19/06/2023 | 19/06/2023 | TAMRALIPTA GUCHHA SAMITY | 1.35 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00261/2023-2024 | BP-2023-24-136 | 19/06/2023 | 19/06/2023 | SRIRAMAKRISHNA GUCHHA SAMITY | 1.35 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00729/2023-2024 | BP-2023-24-412 | 26/09/2023 | 26/09/2023 | VIVEKANANDA YUBA PARISHADISP | 1.35 | 0 | 0 | 0
18 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. |  |  | BILL/00037/2023-2024 | BP-2023-24-30 | 29/04/2023 | 29/04/2023 | SRIRAMAKRISHNA GUCHHA SAMITY | 1.32 | 0 | 0 | 0
19 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00264/2023-2024 | BP-2023-24-139 | 19/06/2023 | 19/06/2023 | VIVEKANANDA YUBA PARISHADISP | 1.35 | 0 | 0 | 0
20 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Bill for contingency expenses of Gram Mangal Water testing laboratory for the period of April-2022 to March-2023 |  |  | BILL/00451/2023-2024 | BP-2023-24-259 | 17/08/2023 | 17/08/2023 | GRAMMANGAL WATER TESTING LAB | 0.75 | 0 | 0 | 0
21 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Bill for contingency expenses of Lokajagaran Water testing laboratory for the period of April-2022 to March-2023 |  |  | BILL/00454/2023-2024 | BP-2023-24-262 | 17/08/2023 | 17/08/2023 | LOKAJAGARAN | 0.75 | 0 | 0 | 0
22 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00262/2023-2024 | BP-2023-24-137 | 19/06/2023 | 19/06/2023 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.35 | 0 | 0 | 0
23 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. |  |  | BILL/00041/2023-2024 | BP-2023-24-35 | 29/04/2023 | 29/04/2023 | ABHYUDAYA HALDIA | 1.32 | 0 | 0 | 0
24 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. |  |  | BILL/00035/2023-2024 | BP-2023-24-28 | 29/04/2023 | 29/04/2023 | TAMRALIPTA GUCHHA SAMITY | 1.32 | 0 | 0 | 0
25 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from January, 2023 to March, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00260/2023-2024 | BP-2023-24-135 | 19/06/2023 | 19/06/2023 | LOKAJAGARAN | 1.35 | 0 | 0 | 0
26 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00730/2023-2024 | BP-2023-24-413 | 26/09/2023 | 26/09/2023 | GRAMMANGAL WATER TESTING LAB | 1.35 | 0 | 0 | 0
27 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00731/2023-2024 | BP-2023-24-414 | 26/09/2023 | 26/09/2023 | SRIRAMAKRISHNA GUCHHA SAMITY | 1.35 | 0 | 0 | 0
28 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. |  |  | BILL/00040/2023-2024 | BP-2023-24-34 | 29/04/2023 | 29/04/2023 | VIVEKANANDA YUBA PARISHADISP | 1.32 | 0 | 0 | 0
29 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. |  |  | BILL/00036/2023-2024 | BP-2023-24-32 | 29/04/2023 | 29/04/2023 | LOKAJAGARAN | 1.32 | 0 | 0 | 0
30 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Bill for contingency expenses of Tamralipta Guchha Samity Water testing laboratory for the period of April-2022 to March-2023 |  |  | BILL/00449/2023-2024 | BP-2023-24-257 | 17/08/2023 | 17/08/2023 | TAMRALIPTA GUCHHA SAMITY | 0.75 | 0 | 0 | 0
31 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Bill for contingency expenses of Abhyudaya- Haldia Water testing laboratory for the period of April-2022 to March-2023 |  |  | BILL/00450/2023-2024 | BP-2023-24-258 | 17/08/2023 | 17/08/2023 | ABHYUDAYA HALDIA | 0.75 | 0 | 0 | 0
32 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00725/2023-2024 | BP-2023-24-408 | 26/09/2023 | 26/09/2023 | TAMRALIPTA GUCHHA SAMITY | 1.35 | 0 | 0 | 0
33 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium bill for Chemist, Bacteriologist and Laboratory Assistant for NGO Managed laboratory for the period from September, 2022 to December, 2022. |  |  | BILL/00038/2023-2024 | BP-2023-24-31 | 29/04/2023 | 29/04/2023 | BHAGWANPURII VIVEKANANDA KALYAN PARISHAD | 1.32 | 0 | 0 | 0
34 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Bill for contingency expenses of Sri Ramkrishna Guchha Samity Water testing laboratory for the period of April-2022 to March-2023 |  |  | BILL/00452/2023-2024 | BP-2023-24-260 | 17/08/2023 | 17/08/2023 | SRIRAMAKRISHNA GUCHHA SAMITY | 0.75 | 0 | 0 | 0
35 | PURBA MEDINIPUR |  | Tamluk Division | Operation charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. | SM/11816 | Support-WQMSP | Honorarium Bill for Chemist, Bacteriologist & Laboratory Assistant under NGO managed laboratory for the period from April, 2023 to June, 2023 under Tamluk Division, PHE Dte. |  |  | BILL/00726/2023-2024 | BP-2023-24-409 | 26/09/2023 | 26/09/2023 | LOKAJAGARAN | 1.35 | 0 | 0 | 0
Total | [13 empty] | 90.14 | 50.45 | 55.96