## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11859 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001907/2022-2023 | 808/W/MMD | 24/03/2023 | 20/09/2023 | SUJOY RANJAN BHOWMICK | 13.58 | 8.29 | 61.02 | 60
2 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11859 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 347/TD | 26/04/2023 | 26/04/2023 | Resource Division | 4.86 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11859 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 27/09/2022 | AQUATECH ENGINEERS | 55.36 | 0 | 0 | 100
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11859 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
5 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11859 | Augmentation | Dismantling & Re-Construction of Boundary Wall and Land Filling at 2nd TW site for Site Preparation for Lowering of Replacement Tube Well at Paschimbetya PWSS for within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000458/2023-2024 | 1495/TD | 17/07/2023 | 01/08/2023 | PULAK KUMAR SAMANTA | 4.84 | 0 | 0 | 30
Total | [13 empty] | 80.75 | 8.29 | 10.27