## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11860 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube well of 1st Tubewell at Mouza- Baliarpur, JL. No. -358 for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method of Boosting Tube well of 3rd Tubewell at Mouza- Madhusudhanbar, JL. No. 365, Plot No. 237 - for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Mouza -Bhaitghar, JL No. - 415, Plot No. -287, Contai- III Block of Kanaidighi Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000252/2022-2023 | 1051/TD | 18/08/2022 | 27/09/2022 | AQUATECH ENGINEER | 54.66 | 16.89 | 30.91 | 32
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11860 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 1st Tube Well and 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block Contai I,under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000170/2023-2024 | 1413/W/MMD | 02/06/2023 | 29/11/2023 | RUBY ENTERPRISE | 27.17 | 13.44 | 49.47 | 80
3 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11860 | Augmentation | Laying Rising Main, Construction of Boundary wall at 3rd Tube Well Boosting Site of Damudarpur PWSS in Contai-I within Contai Sub-Division of Tamluk Division,PHE Dte. {Length-44.00 mtr.} (For Low Land) | Assistant Engineer | Junior Engineer | ORD/000486/2023-2024 | 1576/TD | 19/07/2023 | 18/08/2023 | M/S MONDAL CONSTRUCTION & CO. | 14.04 | 11.85 | 84.41 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11860 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 356/TD | 26/04/2023 | 26/04/2023 | Resource Division | 11.65 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well & 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11860 | Augmentation | Electric quotation for Damodarpur PWSS Tube Well-III WS Scheme (Ref. ID - 203911304) |  |  | BILL/00317/2022-2023 | BP-2022-23-136 | 20/03/2023 | 20/03/2023 | WBSEDCL | 0.37 | 0 | 0 | 0
Total | [13 empty] | 107.89 | 42.18 | 39.1