## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11861 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 361/TD | 26/04/2023 | 26/04/2023 | Resource Division | 4.86 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11861 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 27/09/2022 | AQUATECH ENGINEERS | 55.36 | 11.46 | 20.71 | 100
3 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11861 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block ¿ Deshopran under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001747/2022-2023 | 643/W/MMD | 20/03/2023 | 16/09/2023 | K.S.P. ENTERPRISE | 13.57 | 11.31 | 83.35 | 85
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11861 | Augmentation | Quotation for new service connection at TW-III of Baharchandberia ws scheme under MMD, PHE Dte, Block-Conai-II, MARISHDA CCC Application no-2004763702 Con ID-204323627 |  |  | BILL/01232/2024-2025 | BP-2024-25-286 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.48 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11861 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11861 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF JULY'2024 UNDER HESD, PHE DTE |  |  | BILL/04359/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.21 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11861 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF MAY'2025 UNDER HESD, PHE DTE |  |  | BILL/04373/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.21 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11861 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/HESD DATED-28.08.2024. FOR THE MONTH OF JUNE'2025 UNDER HESD, PHE DTE |  |  | BILL/04370/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.2 | 0 | 0 | 0
Total | [13 empty] | 81.99 | 22.77 | 27.78