## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11862 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 345/TD | 26/04/2023 | 26/04/2023 | Resource Division | 9.11 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11862 | Augmentation | Electric quotation for Barasubarnanagar PWSS Tube Well- III in connection Mukundapur CCC (2004188348) |  |  | BILL/00059/2022-2023 | BP-2022-23-109 | 01/03/2023 | 01/03/2023 | WBSEDCL | 0.5 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11862 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 27/09/2022 | AQUATECH ENGINEERS | 55.36 | 13.05 | 23.57 | 100
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11862 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Boosting Tube Well No. III for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District.under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/000133/2023-2024 | 1354/W/MMD | 24/05/2023 | 20/11/2023 | SOUMEN ELECTRIC | 13.57 | 12.5 | 92.1 | 40
5 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11862 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Barasubarnanagar W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000210/2023-2024 | 472/TD | 10/05/2023 | 09/07/2023 | JASODA ENTERPRISE | 3.83 | 3.58 | 93.47 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11862 | Augmentation | Laying of 150 mm dia & 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at Replacement of 1st Tube Well & 1(One) no. Boosting Tube Well of Barasubarnanagar & its adjoining mouzas Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 471/TD | 10/05/2023 | 09/06/2023 | JASODA ENTERPRISE | 4.01 | 1.62 | 40.31 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11862 | Augmentation | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 31/05/2025 | AQUATECH ENGINEERS | 45.52 | 13.07 | 28.72 | 98
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11862 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001343/2022-2023 | 36/W/MMD | 04/01/2023 | 30/12/2023 | SOUMEN ELECTRIC | 13.57 | 12.8 | 94.33 | 80
Total | [13 empty] | 145.48 | 56.62 | 38.92