## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Laying distribution system pipe line, accommodate FHTC(764 nos), Laying Rising Main under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000141/2023-2024 | 282/TD | 20/04/2023 | 25/05/2026 | NARAYAN MANDAL | 92.86 | 61.98 | 66.74 | 65
2 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Laying distribution system pipe line, accommodate FHTC(700 nos),Construction of switch room cum cholorine room(2nd T/W site) , Construction of Boundary Wall (2nd t/w site) under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000288/2023-2024 | 581/TD | 16/05/2023 | 21/06/2026 | NARAYAN MANDAL | 139.9 | 99.14 | 70.87 | 76
3 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Soil investigation & Construction of RCC over Head Reservoir of capacity 300 cum and staging height 20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), under JJM with allied work for Harshankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000295/2023-2024 | 584/TD | 16/05/2023 | 12/11/2023 | RAJ KUMAR SINGHA | 112.97 | 26.5 | 23.45 | 2
4 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001705/2022-2023 | 626/W/MMD | 20/03/2023 | 09/03/2025 | DEBJYOTI BASU | 23.7 | 11.01 | 46.45 | 35
5 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Laying distribution system pipe line, accommodate FHTC(500 nos),Construction of switch room cum cholorine room(H/W site) , Construction of Boundary Wall (H/W site) under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000298/2023-2024 | 590/TD | 17/05/2023 | 28/07/2025 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 88.84 | 52.65 | 59.26 | 30
6 | PURBA MEDINIPUR | Tamluk | Central Drilling | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 230 Mtrs. Depth) by utilising Departmental Machineries for Harashankar W/S Scheme, Tamluk Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000521/2022-2023 | 2114/CDD | 02/03/2023 | 01/04/2023 | PADMA ENGINEERING & CO. | 17.76 | 15.45 | 87.01 | 100
7 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Material Requisition To Resource Division |  |  | RTOR000301/2022-2023 | 3005/TD | 27/02/2023 | 27/02/2023 | Resource Division | 16.42 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | M.S. Structure for canel crossing for laying 150 mm DI (K9) Rising main and 200 mm DI (K7) pipes ( Nodal 379-382 ) of Harasankar PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Canal Length- = 20.00 mtr. ,Number of crossing -2 nos | Assistant Engineer | Junior Engineer | ORD/000300/2024-2025 | 3059/TD | 19/09/2024 | 06/06/2026 | NARAYAN MANDAL | 8.28 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | M.S. Structure for canel crossing for laying 110 mm OD uPVC pipe of Harasankar PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001197/2023-2024 | 825/TD | 05/03/2024 | 25/03/2024 | NARAYAN MANDAL | 4.21 | 3.02 | 71.65 | 10
10 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Laying distribution system pipe line, accommodate FHTC construction of switch room cum chlorine room (2nd T/W site), construction of Boundary wall (2nd T/W site), under JJM with allied work for Harasankar PWSS within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001206/2023-2024 | 887/TD | 06/03/2024 | 10/04/2024 | NARAYAN MANDAL | 4.09 | 4.09 | 99.99 | 100
11 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Harasankar W/S scheme H/W site Application No.-2004562746 Ref.-204191037 |  |  | BILL/03465/2023-2024 | BP-2023-24-588 | 02/02/2024 | 02/02/2024 | WBSEDCL | 5.1 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Tamluk | Tamluk Division | HARASHANKAR AND ITS ADJOINING MOUJAS PWSS | SM/11881 | New | Laying of 90 mm OD HDPE pipe line at Harasankar village ( Booth no -72 ) as per revised drawing of Harasankar PWSS under Tamluk Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000593/2024-2025 | 565/TD | 17/02/2025 | 18/04/2025 | MMS CONSTRUCTIONS PVT. LTD. | 29.77 | 0 | 0 | 100
Total | [13 empty] | 543.9 | 273.83 | 50.35