## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | KURPAI AND ADJOINING MOUJAS PWSS | SM/11882 | New | Material Requisition To Resource Division |  |  | RTOR000219/2022-2023 | 2679/TD | 06/02/2023 | 06/02/2023 | Resource Division | 19.42 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | KURPAI AND ADJOINING MOUJAS PWSS | SM/11882 | New | Quotation Bill for Kurpai T/W-II Tamluk CCC Application No=2005004861 Reference ID=204470853 |  |  | BILL/03678/2024-2025 |  | 18/12/2024 | 18/12/2024 | WBSEDCL | 5.23 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | KURPAI AND ADJOINING MOUJAS PWSS | SM/11882 | New | Kurpai W/S scheme H/W site. Application.-2004547144 Ref.-204177947 |  |  | BILL/03301/2023-2024 | BP-2023-24-547 | 15/01/2024 | 15/01/2024 | WBSEDCL | 8.64 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Tamluk Division | KURPAI AND ADJOINING MOUJAS PWSS | SM/11882 | New | Sinking of Tube Well ,Laying distribution system pipe line, accommodate FHTC(1309 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of 200 Cum. capacity RCC over Head Reservoir and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Kurpai PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000231/2023-2024 | 461/TD | 04/05/2023 | 01/11/2025 | MAA ANANDAMAYEE | 396.25 | 0 | 0 | 75
5 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | KURPAI AND ADJOINING MOUJAS PWSS | SM/11882 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KURPAI AND ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000085/2023-2024 | 1271/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 22.69 | 0 | 0 | 35
6 | PURBA MEDINIPUR | Tamluk | Tamluk Division | KURPAI AND ADJOINING MOUJAS PWSS | SM/11882 | New | Laying Distribution System (missing nodal as per drawing) of 110 mm dia & 125 mm dia HDPE pipe line, Drumpsheet Pilling and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 110 mm dia (sec 203-206, 132-133, 437-443, 639-638, 705-713 and 183-155) of pipe line of Kurpai Water Supply Scheme of Tamluk Sub-Division under Tamluk Division P.H.E. Dte. | Assistant Engineer | Junior Engiener | ORD/000536/2024-2025 | 201/TD | 15/01/2025 | 11/12/2025 | MAA ANANDAMAYEE | 36.38 | 0 | 0 | 80
Total | [13 empty] | 488.61 | 0 | 0