## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | SM/11883 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHIA AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. |  |  | ORD/001695/2022-2023 | 622/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 22.81 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | SM/11883 | New | Soil investigation & Construction of RCC Over Head of capacity 200 cum and staging height 20.00 mtr as per Deptt. Drawing ( Intze type with pile foundation), under JJM with allied work for Nilkanthia_PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division,PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000140/2023-2024 | 281/TD | 20/04/2023 | 17/10/2023 | HARIPADA PATTANAYAK | 93.35 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Tamluk | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | SM/11883 | New | Material Requisition To Resource Division |  |  | RTOR000300/2022-2023 | 3006/TD | 27/02/2023 | 27/02/2023 | Resource Division | 16.01 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | SM/11883 | New | Laying distribution system pipe line, accommodate FHTC (877 nos),Construction of switch room cum cholorine room , Laying of rising main, Construction of Boundary Wall under JJM with allied work for Nilkanthia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000392/2023-2024 | 1065/TD | 08/06/2023 | 15/02/2025 | SUDIPTA ROY | 123.48 | 0 | 0 | 26
5 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | SM/11883 | New | Quotation Bill for Nilkunthia W/S Scheme T/W-I Application No=2004684512 Reference ID=204275851 |  |  | BILL/00576/2024-2025 | BP-2024-25-102 | 26/04/2024 | 26/04/2024 | WBSEDCL | 4.02 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Tamluk | Central Drilling | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | SM/11883 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
7 | PURBA MEDINIPUR | Tamluk | Central Drilling | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | SM/11883 | New | Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000009/2024-2025 | 138/S&WSD | 26/06/2024 | 25/12/2024 | NAGENDRA PATRA | 0.86 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Tamluk | Tamluk Division | NILKANTHIA AND ITS ADJOINING MOUJAS PWSS | SM/11883 | New | Sinking of 250 x 150 mm Dia and 230m deep tubewell ( at 2nd tube well site) Drilling by Direct Rotary method with 150 dia. UPVC. Strainer of 30m.length all complete including cost of materials for Nilkunthia Water Supply Scheme under Tamluk Block under Tamluk Sub Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000578/2024-2025 | 456/TD | 04/02/2025 | 24/02/2025 | PRANTIK DRILLING AGENCY | 12.58 | 0 | 0 | 0
Total | [13 empty] | 21612.89 | 0 | 0