## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | BARNAN AND ITS ADJOINING MOUJAS PWSS | SM/11884 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARNAN AND ITS ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001699/2022-2023 | 624/W/MMD | 20/03/2023 | 01/09/2025 | DEBJYOTI BASU | 23.7 | 15.07 | 63.6 | 50
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS | SM/11884 | New | Material Requisition To Resource Division |  |  | RTOR000274/2022-2023 | 2684/TD | 06/02/2023 | 06/02/2023 | Resource Division | 19.64 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS | SM/11884 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Barnan PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000164/2024-2025 | 2076/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS | SM/11884 | New | Land filling with silver sand and land development of approach road and other side at 1st. & 2nd T/W site Barnan W/S Scheme of Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2024-2025 | 2182/TD | 08/07/2024 | 22/07/2024 | S.D. CONSTRUCTION | 3.91 | 3.91 | 99.98 | 100
5 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS | SM/11884 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 82//TD | 05/01/2024 | 05/01/2024 | Resource Division | 6.85 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | BARNAN AND ITS ADJOINING MOUJAS PWSS | SM/11884 | New | Quotation Bill for Barnan Water supply Scheme Tubewell No-I Application No=2004754441 Reference ID=204318380 |  |  | BILL/01164/2024-2025 | BP-2024-25-266 | 12/06/2024 | 12/06/2024 | WBSEDCL | 8.5 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | BARNAN AND ITS ADJOINING MOUJAS PWSS | SM/11884 | New | Quotation Bill for Barnan Water supply Scheme Tubewell No-II Application No=2004756795 Reference ID=204319871 |  |  | BILL/01163/2024-2025 | BP-2024-25-267 | 12/06/2024 | 12/06/2024 | WBSEDCL | 5.48 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | BARNAN AND ITS ADJOINING MOUJAS PWSS | SM/11884 | New | Construction of 1(One) nos M.S. Structure over irrigation canal to support 200 mm dia. DI K-7 distribution pipe under Barnan Water Supply Scheme at NP 7-10 under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte.(Each length=24.00 Mtr ) | Assistant Engineer | Junior Engineer | ORD/000401/2025-2026 | 2147/TD | 18/08/2025 | 17/09/2025 | GLOBAL TRADE | 3.74 | 0 | 0 | 100
Total | [13 empty] | 72.78 | 19.94 | 27.39