## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS | SM/11885 | New | Material Requisition To Resource Division |  |  | RTOR000297/2022-2023 | 3008/TD | 27/02/2023 | 27/02/2023 | Resource Division | 20.18 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk | Tamluk Division | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS | SM/11885 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1127 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height 20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Mamudpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000402/2023-2024 | 1094/TD | 08/06/2023 | 30/06/2026 | SUJATA CONSTRUCTION | 315 | 83.66 | 26.56 | 20
3 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS | SM/11885 | New | Quotation bill for new service connection at TW-I of Mamudpur W/S scheme under MMD PHE Dte. Block-Tamluk Tamluk CCC Application No.-2004916353 Consumer ID.-204409669 |  |  | BILL/02974/2024-2025 | C112402770847 | 05/11/2024 | 05/11/2024 | WBSEDCL | 3.64 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS | SM/11885 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001697/2022-2023 | 623/W/MMD | 20/03/2023 | 30/06/2026 | BHABANI PRASAD MANNA | 23.7 | 0 | 0 | 40
5 | PURBA MEDINIPUR | Tamluk | Tamluk Division | MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS | SM/11885 | New | Land development at Head work site and 2nd Tube well site of Mamudpur Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000141/2024-2025 | 1921/TD | 07/06/2024 | 15/11/2024 | SAYAN CONSTRUCTION | 7.12 | 0 | 0 | 95
Total | [13 empty] | 369.64 | 83.66 | 22.63