## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | PUTPUTIA PWSS | SM/11886 | New | Material Requisition To Resource Division |  |  | RTOR000222/2022-2023 | 2677/TD | 06/02/2023 | 06/02/2023 | Resource Division | 23.37 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | PUTPUTIA PWSS | SM/11886 | New | Electric Quotation for PUTPUTIA Head Work Water Supply Scheme T/W-I, (Ref. ID-204094476) |  |  | BILL/02679/2023-2024 | BP-2023-24-270 | 10/10/2023 | 10/10/2023 | WBSEDCL | 5.52 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | PUTPUTIA PWSS | SM/11886 | New | Electric Quotation for PUTPUTIA Water Supply Scheme , T/W-II (Ref. ID-204075888) |  |  | BILL/02182/2023-2024 | BP-2023-24-240 | 12/09/2023 | 12/09/2023 | WBSEDCL | 4.59 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | PUTPUTIA PWSS | SM/11886 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PUTPUTIA PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001691/2022-2023 | 620/W/MMD | 20/03/2023 | 01/09/2025 | M/S B.M. ELECTRICAL | 22.81 | 0 | 0 | 35
Total | [13 empty] | 56.29 | 0 | 0