## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | PUTPUTIA PWSS | SM/11886 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1670 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 250 cum and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Putputia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000073/2023-2024 | 130/TD | 10/04/2023 | 24/02/2026 | TARUN KOLEY | 483.49 | 237.21 | 49.06 | 70
2 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | PUTPUTIA PWSS | SM/11886 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PUTPUTIA PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001691/2022-2023 | 620/W/MMD | 20/03/2023 | 01/09/2025 | M/S B.M. ELECTRICAL | 22.81 | 19.81 | 86.85 | 35
3 | PURBA MEDINIPUR | Tamluk | Tamluk Division | PUTPUTIA PWSS | SM/11886 | New | Material Requisition To Resource Division |  |  | RTOR000222/2022-2023 | 2677/TD | 06/02/2023 | 06/02/2023 | Resource Division | 23.37 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | PUTPUTIA PWSS | SM/11886 | New | Electric Quotation for PUTPUTIA Water Supply Scheme , T/W-II (Ref. ID-204075888) |  |  | BILL/02182/2023-2024 | BP-2023-24-240 | 12/09/2023 | 12/09/2023 | WBSEDCL | 4.59 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | PUTPUTIA PWSS | SM/11886 | New | Electric Quotation for PUTPUTIA Head Work Water Supply Scheme T/W-I, (Ref. ID-204094476) |  |  | BILL/02679/2023-2024 | BP-2023-24-270 | 10/10/2023 | 10/10/2023 | WBSEDCL | 5.52 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | PUTPUTIA PWSS | SM/11886 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision and monitoring of different ongoing piped water supply scheme for covering Tamluk Sub Division and its adjacent Sub -Divisions under JJM Programe for the office of Assistant Engineer, under Haldia Electrical Sub Division. P.H.E. Dte., under Purba Midnapore under MMD PHE Dte. w.e.f.-w.e.f 01-09-2025 to 31-08-2026. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2025-2026 | 875/HESD | 29/08/2025 | 29/08/2026 | S.S.GHORAI | 4.78 | 0 | 0 | 40
Total | [13 empty] | 544.56 | 257.01 | 47.2