## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | SM/11887 | Augmentation | Providing drilling crew and other allied works for construction of TW (300mm x 200mm x 260 mtrs. depth) by utilising Departmental machineries for uttar Khasda WS Scheme (TW-III) contai-I block under Purba midnapore District , CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000344/2022-2023 | 1345/CDD | 24/11/2022 | 24/12/2022 | MENAKA ENTERPRISE | 19.77 | 14.04 | 71.01 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | SM/11887 | Augmentation | Electric Quotation for UTTAR KHASDA Water Supply SchemeT/W-III (Ref. ID-204049279) |  |  | BILL/01636/2023-2024 | BP-2023-24-136 | 27/07/2023 | 27/07/2023 | WBSEDCL | 2.59 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | SM/11887 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Uttar Khasda Water Supply Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000865/2023-2024 | 233/TD | 10/01/2024 | 10/03/2024 | KAMAL KUMAR BERA | 4.02 | 3.82 | 94.92 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | SM/11887 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Uttar Khasda W/S Scheme within Contai- I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000436/2023-2024 | 1419/TD | 12/07/2023 | 11/08/2023 | PULAK KUMAR SAMANTA | 8.31 | 7.06 | 85.04 | 100
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | SM/11887 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001736/2022-2023 | 638/W/MMD | 20/03/2023 | 30/04/2025 | SOUMEN ELECTRIC | 13.57 | 9.66 | 71.16 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | SM/11887 | Augmentation | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1 (One) no. Boosting Tube Well of Uttar Khasda & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000864/2023-2024 | 234/TD | 10/01/2024 | 03/02/2025 | THE GODFATHER TRADING COMPANY | 3.44 | 0 | 0 | 100
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. | SM/11887 | Augmentation | Uttar Khasda W/S scheme T/W-III Application-no.-2004381822 Ref.-204049279 |  |  | BILL/03165/2023-2024 | C072340248980 | 31/01/2025 | 31/01/2025 | WBSEDCL | 0 | 0 | 0 | 0
Total | [13 empty] | 51.72 | 34.58 | 66.87