## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Central Drilling | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11896 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Amtalia W/S Scheme (TW-III) , Deshpran Block under Purba Midnapore District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000516/2022-2023 | 1230/CDD | 16/11/2022 | 16/12/2022 | PADMA ENGINEERING & CO. | 19.11 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11896 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001729/2022-2023 | 636/W/MMD | 20/03/2023 | 16/09/2023 | SOUMEN ELECTRIC | 13.57 | 0 | 0 | 60
3 | PURBA MEDINIPUR |  | Tamluk Division | 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. | SM/11896 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Amtalia W/S Scheme within Contai- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000437/2023-2024 | 1420/TD | 12/07/2023 | 11/08/2023 | PARIA ENTERPRISE | 9.47 | 0 | 0 | 0
Total | [13 empty] | 42.15 | 0 | 0