## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | KHARUI AND ADJOINING MOUZAS PWSS | SM/11945 | New | Material Requisition To Resource Division |  |  | RTOR000273/2022-2023 | 2685/TD | 06/02/2023 | 06/02/2023 | Resource Division | 73.85 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | KHARUI AND ADJOINING MOUZAS PWSS | SM/11945 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kharui PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000165/2024-2025 | 2077/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | KHARUI AND ADJOINING MOUZAS PWSS | SM/11945 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 136/TD | 05/01/2024 | 05/01/2024 | Resource Division | 15.86 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS | SM/11945 | New | Quotation Bill for Kharui W/S Scheme T/W-II Application No=2004614098 Reference ID=204225097 |  |  | BILL/04335/2023-2024 | BP-2023-24-802 | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.72 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS | SM/11945 | New | Quotation Bill for Kharui W/S Scheme H/W Site Application No=2004624417 Reference ID=204231697 |  |  | BILL/04336/2023-2024 | BP-2023-24-801 | 11/03/2024 | 11/03/2024 | WBSEDCL | 4.66 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS | SM/11945 | New | Additional Quotation for Kharui Water Supply Scheme T/W-I Kolaghat CCC, Block-Sahaid Matangini Reference ID=860298136 Application ID=100000106136 Quotation Date=23.04.2024 |  |  | BILL/00694/2024-2025 | BP-2024-25-144 | 09/05/2024 | 09/05/2024 | WBSEDCL | 0.62 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS | SM/11945 | New | ADDITIONAL CHARGE (ESCAL CHARGE-5%) FOR PO MODIFICATION TO REMOVE ROW AT THE TIME OF EXECUTATION THE Quotation bill for T/W NO-I OF KHARUI W/S SCHEME under MMD,PHE,Dte. WBSEDCL SUPPLY OFFICE: Kolaghat C.C.C Ref. Memo No- KCCC/T-08/DATED-29.11.2024/265 DT. 29/11/2024 APPLICATION ID: 100000124382 REFERENCE Id- 860319442 |  |  | BILL/03373/2024-2025 | C122421497101 | 16/12/2024 | 16/12/2024 | WBSEDCL | 0.23 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | KHARUI AND ADJOINING MOUZAS PWSS | SM/11945 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHARUI AND ADJOINING MOUZAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001703/2022-2023 | 625/W/MMD | 20/03/2023 | 01/04/2025 | DEBJYOTI BASU | 23.7 | 15.07 | 63.6 | 90
Total | [13 empty] | 123.58 | 16.02 | 12.97