## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Tamluk Division | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | SM/11946 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(5198nos), Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of different capacity as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Chawrakalganda PWSS & Mirikpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000211/2023-2024 | 433/TD | 03/05/2023 | 27/01/2026 | ARABINDA GHOSH | 1233.42 | 0 | 0 | 65
2 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | SM/11946 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRIKPUR AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001750/2022-2023 | 644/W/MMD | 20/03/2023 | 07/04/2025 | SOUMEN ELECTRIC | 27.17 | 23.4 | 86.14 | 80
3 | PURBA MEDINIPUR | Tamluk | Tamluk Division | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | SM/11946 | New | Material Requisition To Resource Division |  |  | RTOR000221/2022-2023 | 2678/TD | 06/02/2023 | 06/02/2023 | Resource Division | 38.97 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Tamluk Division | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | SM/11946 | New | Work Order for Land development at Head Work Site of Mirikpur Water Supply Scheme within Tamluk Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000181/2024-2025 | 2252/TD | 15/07/2024 | 21/10/2024 | GHOSH ENTERPRISE | 4.07 | 0 | 0 | 100
5 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | SM/11946 | New | Mirikpur W/S scheme H/W site Tw-I Application.-2004547150 Ref.-204177955 |  |  | BILL/03299/2023-2024 | BP-2023-24-545 | 15/01/2024 | 15/01/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | SM/11946 | New | Mirikpur W/S scheme H/W site Tw-II Application.-2004547153 Ref.-204177965 |  |  | BILL/03300/2023-2024 | BP-2023-24-546 | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.21 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Tamluk | Tamluk Division | MIRIKPUR AND ITS ADJOINING MOUJAS PWSS | SM/11946 | New | Canal crossing for laying HDPE pipes of Mirikpur PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Nodal Point J-512 to J-517 ) Canal Length- =30.00 mtr. Number of crossing -1 nos | Assistant Engineer |  | ORD/000582/2024-2025 | 459/TD | 04/02/2025 | 01/03/2025 | GHOSH ENTERPRISE | 6.25 | 0 | 0 | 0
Total | [13 empty] | 1317.79 | 23.4 | 1.78