## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Material Requisition To Resource Division |  |  | RTOR000299/2022-2023 | 3007/TD | 27/02/2023 | 27/02/2023 | Resource Division | 18.84 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001693/2022-2023 | 621/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 22.81 | 0 | 0 | 35
3 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1435 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Harashankar Khamarchak PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000372/2023-2024 | 907/TD | 01/06/2023 | 31/01/2025 | HARIPADA PATTANAYAK | 371.31 | 0 | 0 | 50
4 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Harasankarpur Khamarchak W/S scheme T/W-II Application No.-2004586186, Ref ID.-204209423 Date of quotation .-06/02/2024 New connection. |  |  | BILL/03701/2023-2024 | BP-2023-24-683 | 15/02/2024 | 15/02/2024 | WBSEDCL | 4.35 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | payment for Wayleave plan & survey charges SER-KGP-2024-WL-95 |  |  | BILL/00487/2024-2025 | BP-2024-25-188 | 14/06/2024 | 14/06/2024 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-95) |  |  | BILL/00691/2024-2025 | BP-2024-25-298 | 30/07/2024 | 30/07/2024 | FA & CAO, S.E. RAILWAY, GRC. | 6.08 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Quotation Bill for Harasankar Khamarchak H/W Site Block=Sahid Matangini Application No=2004626478 Reference ID=204233282 |  |  | BILL/04340/2023-2024 | BP-2023-24-803 | 11/03/2024 | 11/03/2024 | WBSEDCL | 4.36 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | M.S. Structure for canel crossing for laying 90 mm dia pipe of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Nodal Point 242-243, 314-315,356-343 & 88A-128 ) Canal Length- = 14.00 mtr. Number of crossing -4 | Assistant Engineer | Junior Engineer | ORD/000331/2024-2025 | 3290/TD | 05/10/2024 | 04/11/2024 | BAGLAMUKHI SECURITY SERVICE | 9.39 | 0 | 0 | 100
9 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Canal crossing, land development, dismentling concrete and restoration work,dram sheet walling of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub- Division of Tamluk division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2024-2025 | 3140/TD | 26/09/2024 | 26/10/2024 | BAGLAMUKHI SECURITY SERVICE | 17.81 | 0 | 0 | 100
Total | [13 empty] | 455.05 | 0 | 0