## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Material Requisition To Resource Division |  |  | RTOR000299/2022-2023 | 3007/TD | 27/02/2023 | 27/02/2023 | Resource Division | 18.84 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001693/2022-2023 | 621/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 22.81 | 21.15 | 92.73 | 35
3 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1435 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Harashankar Khamarchak PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000372/2023-2024 | 907/TD | 01/06/2023 | 26/01/2026 | HARIPADA PATTANAYAK | 371.31 | 201.64 | 54.31 | 50
4 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Harasankarpur Khamarchak W/S scheme T/W-II Application No.-2004586186, Ref ID.-204209423 Date of quotation .-06/02/2024 New connection. |  |  | BILL/03701/2023-2024 | BP-2023-24-683 | 15/02/2024 | 15/02/2024 | WBSEDCL | 4.35 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | payment for Wayleave plan & survey charges SER-KGP-2024-WL-95 |  |  | BILL/00487/2024-2025 | BP-2024-25-188 | 14/06/2024 | 14/06/2024 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-95) |  |  | BILL/00691/2024-2025 | BP-2024-25-298 | 30/07/2024 | 30/07/2024 | FA & CAO, S.E. RAILWAY, GRC. | 6.08 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Midnapore Mechanical | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Quotation Bill for Harasankar Khamarchak H/W Site Block=Sahid Matangini Application No=2004626478 Reference ID=204233282 |  |  | BILL/04340/2023-2024 | BP-2023-24-803 | 11/03/2024 | 11/03/2024 | WBSEDCL | 4.36 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Jack Pushing of Railway Track Between Raghunathbari to Rajgoda Railway Station on Panskura Tamluk Section of Kharagpur S.E. Railway Division of Purba Medinipur for Harasankar Khamarchak Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 150 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 13/5 & 13/7 and 13/6 & 13/8 within Tamluk Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =60.0 Mtr) Nodal Point 176 TO 183. | Assistant Engineer | Junior Engineer | ORD/001256/2023-2024 | 1070/TD | 16/03/2024 | 03/12/2024 | HARIPADA PATTANAYAK | 73.77 | 0 | 0 | 100
9 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | M.S. Structure for canel crossing for laying 90 mm dia pipe of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Nodal Point 242-243, 314-315,356-343 & 88A-128 ) Canal Length- = 14.00 mtr. Number of crossing -4 | Assistant Engineer | Junior Engineer | ORD/000331/2024-2025 | 3290/TD | 05/10/2024 | 04/11/2024 | BAGLAMUKHI SECURITY SERVICE | 9.39 | 0 | 0 | 100
10 | PURBA MEDINIPUR | Sahid Matangini,Tamluk | Tamluk Division | HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS | SM/11947 | New | Canal crossing, land development, dismentling concrete and restoration work,dram sheet walling of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub- Division of Tamluk division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2024-2025 | 3140/TD | 26/09/2024 | 26/10/2024 | BAGLAMUKHI SECURITY SERVICE | 17.81 | 0 | 0 | 100
Total | [13 empty] | 528.82 | 222.79 | 42.13