## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11949 | Augmentation | Retrofitting to Accommodate 30 nos FHTC under JJM in Sofiabad PWSS Block- Contai-II ( Deshpran) of Tamluk Division, PHE Dte,in the districtof Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000394/2022-2023 | 1427/TD | 26/09/2022 | 11/10/2022 | RELIABLE CONSTRUCTIONS | 1.28 | 1.28 | 100 | 100
2 | PURBA MEDINIPUR |  | Midnapore Mechanical | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11949 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001731/2022-2023 | 637/W/MMD | 20/03/2023 | 16/09/2023 | SOUMEN ELECTRIC | 13.57 | 9.66 | 71.16 | 60
3 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11949 | Augmentation | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Sofiabad W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000235/2023-2024 | 483/TD | 10/05/2023 | 09/07/2023 | BABA LOKNATH CONSTRUCTION | 4.03 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11949 | Augmentation | Laying of 150 mm dia & 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at Replacement of 2nd Tube Well & 1(One) no. Boosting Tube Well of Sofiabad & its adjoining mouzas Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000236/2023-2024 | 482/TD | 10/05/2023 | 30/12/2024 | KAMAL KUMAR BERA | 3.92 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Central Drilling | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11949 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Sofiabad W/S Scheme (T/W-I & II) , Deshpran Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000114/2023-2024 | 856/CDD | 10/07/2023 | 11/08/2024 | MENAKA ENTERPRISE | 29.23 | 0 | 0 | 50
6 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11949 | Augmentation | Instalation of display Board at different work site of Bamunia, Barasubarnagar, Sofiabad, Aladarput Retrofitting PWSS in Contai - II (Deshopran) Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001185/2023-2024 | 2333/CSD | 29/12/2023 | 13/01/2024 | ABHIJIT BERA | 0.83 | 0.83 | 100 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. | SM/11949 | Augmentation | Replacement of Damaged UPVC Pipe Line , FHTC with allied works of Sofiabad PWSS within Contai-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000797/2025-2026 | 3071/TD | 19/12/2025 | 18/04/2026 | BISWA NIRMAN ENTERPRISE. | 3.89 | 0 | 0 | 0
Total | [13 empty] | 56.75 | 11.77 | 20.74