## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000233/2022-2023 | 2616/TD | 02/02/2023 |  | Resource Division | 349.36 | 0 | 0 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000288/2022-2023 | 2641/TD | 02/02/2023 |  | Resource Division | 204.6 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshinchak Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2022-2023 | 51/TD | 05/04/2022 | 25/04/2022 | HORIZEN | 6.01 | 6 | 99.77 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 2638/TD | 13/10/2023 |  | Resource Division | 43.18 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of T/W- III, Zone-I for Dakshin Chak Water Supply Scheme, Block - Haldia under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002726/2023-2024 | 1071/W/MMD | 14/03/2024 | 10/09/2024 | DEBSANKER BHATTACHARYA | 13.59 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Dakshinchak Zone-I Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000820/2023-2024 | 3288/TD | 20/12/2023 | 09/01/2024 | DONA ASSOCIATES | 9.38 | 2.76 | 29.43 | 30
7 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Crossing permission of laying HDPE pipeline along and across of NH-116 of Dakshinchak Zone-II Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000821/2023-2024 | 3287/TD | 20/12/2023 | 09/01/2024 | DONA ASSOCIATES | 10.9 | 2.76 | 25.34 | 30
8 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Zone- II of Tube well-I and II at Dakshin Chak Water supply scheme, Haldia block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001684/2023-2024 | 63/W/MMD | 15/01/2024 | 13/07/2024 | SUJOY RANJAN BHOWMICK | 28.21 | 0 | 0 | 30
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme, Block - Haldia under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001723/2022-2023 | 635/W/MMD | 20/03/2023 | 16/09/2023 | P.K.ENGINEERING | 27.18 | 0 | 0 | 30
10 | PURBA MEDINIPUR |  | Tamluk Division | Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme. | SM/11979 | Augmentation | Sinking of Tube well, Reparing & Renovation of 1st & 2nd Pump House, Construction of New 3rd Tube well site Pump House, Construction of 2 nos Pump House, Soil Investigation Test, Construction of Different Capacity OHR, Laying of Rising main, Laying of Distribution pipe line & FHTC(6512 Nos) works for Augmentation of Dakshinchak Zone- I and Dakshinchak Zone-II Water Supply Scheme under Haldia Sub-Division,of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000428/2023-2024 | 1411/TD | 12/07/2023 | 08/01/2024 | M/S S. S. ENTERPRISE | 1432.04 | 160.46 | 11.2 | 6
Total | [13 empty] | 2124.45 | 171.98 | 8.1