## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sherkhanchak Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2021-2022 | 1477/TD | 03/01/2022 | 23/01/2022 | SANTRA ENTERPRISE. | 4.97 | 4.97 | 99.93 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at Replacement of 1st Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 4th Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000315/2022-2023 | 1223/TD | 07/09/2022 | 17/10/2022 | KALPANA BUILDERS | 71.97 | 17.72 | 24.62 | 48
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 1200/TD | 06/09/2022 | 06/09/2022 | Resource Division | 292.79 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 1199/TD | 06/09/2022 | 06/09/2022 | Resource Division | 44.01 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Electric Quotation for SHERKHANCHAK Water Supply Scheme Z-I, T/W-III (Ref. ID-204040417 ) |  |  | BILL/01637/2023-2024 | BP-2023-24-139 | 27/07/2023 | 27/07/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000398/2022-2023 | 1447/TD | 27/09/2022 | 30/08/2025 | TAPAS SANTRA | 896.61 | 774.33 | 86.36 | 70
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001514/2022-2023 | 358/W/MMD | 09/03/2023 | 05/09/2023 | S.K.ENTERPRISE | 35.55 | 29.45 | 82.85 | 70
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Laying of Balance portion for Distribution pipe line by UPVC pipes with allied works for Sherkhanchak Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000356/2023-2024 | 924/TD | 01/06/2023 | 11/07/2023 | S.D. CONSTRUCTION | 98.88 | 94.52 | 95.59 | 95
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Sherkhanchak Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Sherkhanchak Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Sherkhanchak Zone-I W/S Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ( Location:-Mouza-Baratala, J.L No-29, Plot No-342) iv) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Sherkhanchak Zone-I W/S Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ( Location:-Mouza-Baratala, J.L No-29, Plot No-2543) v) Laying Rising main and other allied works Augmentation of Sherkhanchak Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000439/2023-2024 | 1422/TD | 12/07/2023 | 25/03/2025 | M/S. NEW DINDA ENTERPRISE | 41.06 | 13.22 | 32.19 | 75
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001211/2023-2024 | 977/TD | 13/03/2024 | 07/04/2024 | B. K. ENTERPRISE | 19.16 | 0 | 0 | 100
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Quotation for new service connection at Serkhanchak Zone I w/s scheme PH IV Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004675042, Ref ID 204268872) |  |  | BILL/00291/2024-2025 | BP-2024-25-50 | 18/04/2024 | 18/04/2024 | WBSEDCL | 8.33 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | SM/11984 | Augmentation | Rising main (Balance Portion) with laying of 200mm dia & 150 mm dia DI (K-9) From 2nd Tube Well & 4th Tube Well Site to O.H.R. Site and other allied works for Sherkhanchak Zone-I Water Supply Scheme in Khejuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001212/2023-2024 | 978/TD | 13/03/2024 | 05/02/2025 | M/S. NEW DINDA ENTERPRISE | 7.34 | 0 | 0 | 0
Total | [13 empty] | 1521.22 | 934.2 | 61.41