## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000407/2022-2023 | 1449/TD | 27/09/2022 | 30/06/2026 | AJIT KUMAR SOM | 351.09 | 231.59 | 65.96 | 90
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-E) | Assistant Engineer | Junior Engineer | ORD/000526/2022-2023 | 2012/TD | 06/12/2022 | 31/12/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 18.56 | 3.16 | 17.03 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 2093/TD | 13/12/2022 | 20/08/2026 | LOKENATH ENTERPRISES | 79.14 | 47.5 | 60.02 | 95
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000525/2022-2023 | 2011/TD | 06/12/2022 | 31/12/2022 | DHANANJOY DAS | 38.53 | 9.09 | 23.59 | 25
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000408/2022-2023 | 1448/TD | 27/09/2022 | 23/01/2026 | SNEHESH SEN | 170.64 | 99.16 | 58.11 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-F) | Assistant Engineer | Junior Engineer | ORD/000527/2022-2023 | 2013/TD | 06/12/2022 | 31/12/2022 | CHARUBALA ENTERPRISE | 10.76 | 2.41 | 22.37 | 0
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-G) | Assistant Engineer | Junior Engineer | ORD/000524/2022-2023 | 2096/TD | 13/12/2022 | 28/12/2022 | M/S. PRADIP PRADHAN | 4.18 | 4.18 | 100 | 100
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000323/2021-2022 | 1616/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.16 | 6.16 | 100 | 100
9 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2022-2023 | 1667/TD | 03/11/2022 | 03/11/2022 | Resource Division | 128.58 | 0 | 0 | 0
10 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001933/2022-2023 | 852/W/MMD | 24/03/2023 | 20/09/2023 | ECO ENTERPRISE | 13.47 | 13.3 | 98.7 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Name of Work: Sinking of 02 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000169/2023-2024 | 296/TD | 20/04/2023 | 30/05/2023 | SPG ENTERPRISES | 37.92 | 34.74 | 91.61 | 100
12 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Repairing & renovation of Pump House, construction of boundary wall , Land development, Supply & delivery of different dia D.I. Specials with allied works under JJM for Paniparul (Z-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000601/2023-2024 | 2195/TD | 01/09/2023 | 25/03/2025 | AJIT KUMAR SOM | 48.26 | 0 | 0 | 90
13 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Site cleaning at Head work site of Paniparul (zone-I ) W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000917/2023-2024 | 859/DSD | 01/12/2023 | 04/12/2023 | SOM CONSTRUCTION | 0.36 | 0.36 | 100 | 100
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000281/2022-2023 | 2634/TD | 02/02/2023 | 02/02/2023 | Resource Division | 24.04 | 0 | 0 | 0
15 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Paniparul W/S scheme TW-2 Memo No.-2004516174/Quot/03/1649 application no-2004516174 ref. id-204151561 |  |  | BILL/03147/2023-2024 | BP-2023-24-448 | 19/12/2023 | 19/12/2023 | WBSEDCL | 4.39 | 0 | 0 | 0
16 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Paniparul W/S scheme TW-2 Memo No.-2004516165/Quot/03/1650 application no-2004516165 ref. id-204151594 |  |  | BILL/03146/2023-2024 | BP-2023-24-447 | 19/12/2023 | 19/12/2023 | WBSEDCL | 2.91 | 0 | 0 | 0
17 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying distribution of pipe line, Pump House at 2nd TW site, construction of boundary wall & FHTC -100nos. (Phase-II) with allied works under JJM for Paniparul( Z-I) PWSS within Egra- II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001145/2023-2024 | 565/TD | 15/02/2024 | 26/03/2024 | AJIT KUMAR SOM | 39.83 | 35.73 | 89.71 | 100
18 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at PANIPARUL ZONE - I Water supply scheme, Egra -II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001680/2023-2024 | 58/W/MMD | 15/01/2024 | 09/01/2025 | POLYCON ENGINEERS | 13.92 | 12.32 | 88.47 | 100
Total | [13 empty] | 992.73 | 499.69 | 50.33