## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000323/2021-2022 | 1616/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.16 | 6.16 | 100 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-E) | Assistant Engineer | Junior Engineer | ORD/000526/2022-2023 | 2012/TD | 06/12/2022 | 31/12/2022 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 18.56 | 3.16 | 17.03 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000525/2022-2023 | 2011/TD | 06/12/2022 | 31/12/2022 | DHANANJOY DAS | 38.53 | 9.09 | 23.59 | 25
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-F) | Assistant Engineer | Junior Engineer | ORD/000527/2022-2023 | 2013/TD | 06/12/2022 | 31/12/2022 | CHARUBALA ENTERPRISE | 10.76 | 2.41 | 22.37 | 0
5 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-G) | Assistant Engineer | Junior Engineer | ORD/000524/2022-2023 | 2096/TD | 13/12/2022 | 28/12/2022 | M/S. PRADIP PRADHAN | 4.18 | 4.18 | 100 | 100
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Name of Work: Sinking of 02 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000169/2023-2024 | 296/TD | 20/04/2023 | 30/05/2023 | SPG ENTERPRISES | 37.92 | 34.74 | 91.61 | 100
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2022-2023 | 1667/TD | 03/11/2022 | 03/11/2022 | Resource Division | 128.58 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000281/2022-2023 | 2634/TD | 02/02/2023 | 02/02/2023 | Resource Division | 24.04 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001933/2022-2023 | 852/W/MMD | 24/03/2023 | 20/09/2023 | ECO ENTERPRISE | 13.47 | 13.3 | 98.7 | 100
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Site cleaning at Head work site of Paniparul (zone-I ) W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000917/2023-2024 | 859/DSD | 01/12/2023 | 04/12/2023 | SOM CONSTRUCTION | 0.36 | 0.36 | 100 | 100
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying distribution of pipe line, Pump House at 2nd TW site, construction of boundary wall & FHTC -100nos. (Phase-II) with allied works under JJM for Paniparul( Z-I) PWSS within Egra- II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/001145/2023-2024 | 565/TD | 15/02/2024 | 26/03/2024 | AJIT KUMAR SOM | 39.83 | 35.73 | 89.71 | 100
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Paniparul W/S scheme TW-2 Memo No.-2004516165/Quot/03/1650 application no-2004516165 ref. id-204151594 |  |  | BILL/03146/2023-2024 | BP-2023-24-447 | 19/12/2023 | 19/12/2023 | WBSEDCL | 2.91 | 0 | 0 | 0
13 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Paniparul W/S scheme TW-2 Memo No.-2004516174/Quot/03/1649 application no-2004516174 ref. id-204151561 |  |  | BILL/03147/2023-2024 | BP-2023-24-448 | 19/12/2023 | 19/12/2023 | WBSEDCL | 4.39 | 0 | 0 | 0
14 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 2093/TD | 13/12/2022 | 23/12/2025 | LOKENATH ENTERPRISES | 79.14 | 47.5 | 60.02 | 95
15 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000408/2022-2023 | 1448/TD | 27/09/2022 | 23/01/2026 | SNEHESH SEN | 170.64 | 99.16 | 58.11 | 0
16 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Repairing & renovation of Pump House, construction of boundary wall , Land development, Supply & delivery of different dia D.I. Specials with allied works under JJM for Paniparul (Z-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000601/2023-2024 | 2195/TD | 01/09/2023 | 25/03/2025 | AJIT KUMAR SOM | 48.26 | 0 | 0 | 90
17 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I | SM/12118 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at PANIPARUL ZONE - I Water supply scheme, Egra -II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001680/2023-2024 | 58/W/MMD | 15/01/2024 | 09/01/2025 | POLYCON ENGINEERS | 13.92 | 12.32 | 88.47 | 100
Total | [13 empty] | 641.65 | 268.1 | 41.78