## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS | SM/12129 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001710/2022-2023 | 627/W/MMD | 20/03/2023 | 01/11/2025 | P.K.ENGINEERING | 23.7 | 18.1 | 76.38 | 35
2 | PURBA MEDINIPUR | Tamluk | Tamluk Division | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS | SM/12129 | New | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(5198nos), Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of different capacity as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Chawrakalganda PWSS & Mirikpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000211/2023-2024 | 433/TD | 03/05/2023 | 27/01/2026 | ARABINDA GHOSH | 1233.42 | 423.27 | 34.32 | 65
3 | PURBA MEDINIPUR | Tamluk | Tamluk Division | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS | SM/12129 | New | Material Requisition To Resource Division |  |  | RTOR000223/2022-2023 | 2676/TD | 06/02/2023 | 06/02/2023 | Resource Division | 35.6 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS | SM/12129 | New | Chawrakalganda W/S scheme T/W-I Application No.-2004520328 Ref:-204154822 |  |  | BILL/03168/2023-2024 | BP-2023-24-438 | 18/12/2023 | 18/12/2023 | WBSEDCL | 8.99 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Tamluk | Midnapore Mechanical | CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS | SM/12129 | New | Quotation Bill for Changrakalganda T/W-II Gourangapur CCC Application No=2005011150 Reference ID=204475173 |  |  | BILL/03878/2024-2025 | C012539020054 | 21/01/2025 | 21/01/2025 | WBSEDCL | 3.34 | 0 | 0 | 0
Total | [13 empty] | 1305.05 | 441.37 | 33.82