## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | SM/12130 | New | Material Requisition To Resource Division |  |  | RTOR000276/2022-2023 | 2681/TD | 06/02/2023 | 06/02/2023 | Resource Division | 15.32 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | SM/12130 | New | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 29/02/2024 | S.S.GHORAI | 0.45 | 0.05 | 10.99 | 100
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | SM/12130 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Dakshin Utaspur PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000166/2024-2025 | 2078/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | SM/12130 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 91/TD | 05/01/2024 | 05/01/2024 | Resource Division | 8.11 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | SM/12130 | New | Quotation Bill for Dakshin Usutpur Water Supply Scheme T/W-II Matangini CCC,Block=Sahid Matangini Application No=2004690463 Reference ID=204279652 |  |  | BILL/00665/2024-2025 | BP-2024-25-166 | 15/05/2024 | 15/05/2024 | WBSEDCL | 4.65 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | SM/12130 | New | Quotation Bill for Dakshin Usutpur Water Supply Scheme H/W Site Matangini CCC,Block=Sahid Matangini Application No=2004690460 Reference ID=204279646 |  |  | BILL/00667/2024-2025 | BP-2024-25-167 | 15/05/2024 | 15/05/2024 | WBSEDCL | 3.52 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | SM/12130 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000084/2023-2024 | 1272/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 22.69 | 0 | 0 | 25
8 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS | SM/12130 | New | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 27/08/2024 | S.S.GHORAI | 0.45 | 0 | 0 | 100
Total | [13 empty] | 56.14 | 1 | 1.79