## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AGAR & ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000167/2023-2024 | 1409/W/MMD | 02/06/2023 | 29/11/2023 | M/S B.M. ELECTRICAL | 21.62 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Material Requisition To Resource Division |  |  | RTOR000315/2022-2023 | 3003/TD | 27/02/2023 | 27/02/2023 | Resource Division | 20.51 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Agar PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000163/2024-2025 | 2075/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
4 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 76/TD | 05/01/2024 | 05/01/2024 | Resource Division | 5.13 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Quotation Bill for Agar Water Supply Scheme T/W-II Matangini CCC,Block=Sahid Matangini Application No=2004676891 Reference ID=204270379 |  |  | BILL/00668/2024-2025 | BP-2024-25-168 | 15/05/2024 | 15/05/2024 | WBSEDCL | 0.29 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Quotation Bill for Agar Water Supply Scheme H/W Site Matangini CCC,Block=Sahid Matangini Application No=2004699675 Reference ID=204286135 |  |  | BILL/00669/2024-2025 | BP-2024-25-169 | 15/05/2024 | 15/05/2024 | WBSEDCL | 5.63 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Laying distribution pipe line, Pump House , Boundary Wall ,Rising main , O&M and accommodate FHTC (832 nos) under JJM with allied work for AGAR PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000346/2023-2024 | 850/TD | 31/05/2023 | 01/12/2025 | JAGANNATH MAKAR | 196.83 | 0 | 0 | 60
8 | PURBA MEDINIPUR | Sahid Matangini | Central Drilling | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | AGAR & ADJOINING MOUJAS PWSS | SM/12131 | New | Soil investigation & construction of R.C.C. Elevated Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied works under Agar & its adjoining moujas Water Supply Scheme in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-C) | Assistant Engineer | Junior Engineer | ORD/000418/2023-2024 | 1087/TD | 08/06/2023 | 21/11/2025 | GOUTAM CONSTRUCTION | 75.53 | 0 | 0 | 60
Total | [13 empty] | 21666.26 | 0 | 0