## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | AMARPUR & ADJOINING MOUZAS | SM/12132 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMARPUR and ADJOINING MOUJAS, Block potaspur- I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002029/2022-2023 | 937/W/MMD | 28/03/2023 | 07/03/2025 | MENAKA ENTERPRISE | 22.77 | 13.33 | 58.55 | 50
2 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | AMARPUR & ADJOINING MOUZAS | SM/12132 | New | Sinking of Tube well,Pump House ,Construction of 200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (2655 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Chandpur and Amarpur & its adjoining moujas PWSS within Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000679/2023-2024 | 2705/TD | 20/10/2023 | 30/05/2026 | TAPAS SANTRA | 939.05 | 175.32 | 18.67 | 70
3 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | AMARPUR & ADJOINING MOUZAS | SM/12132 | New | Material Requisition To Resource Division |  |  | RTOR000226/2022-2023 | 2706/TD | 06/02/2023 | 06/02/2023 | Resource Division | 24.84 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | AMARPUR & ADJOINING MOUZAS | SM/12132 | New | Quotation Bill for New Service connection at T/W NO-II Of AMARPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004793608/QUOT/03 DT. 25-06-2024 MEMO NO: AMR/PHE/223 DT. 25-06-2024 Application NO- 2004793608 Application type-New connection Consumer Id- 204340910 |  |  | BILL/01369/2024-2025 | BP-2024-25-373 | 08/07/2024 | 08/07/2024 | WBSEDCL | 4.59 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | AMARPUR & ADJOINING MOUZAS | SM/12132 | New | Quotation Bill for New Service connection at T/W NO-I Of AMARPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743549/QUOT/03 DT. 25-05-2024 Application NO- 2004743549 Application type-New connection Consumer Id- 204312620 |  |  | BILL/01202/2024-2025 | BP-2024-25-318 | 24/06/2024 | 24/06/2024 | WBSEDCL | 3.67 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | AMARPUR & ADJOINING MOUZAS | SM/12132 | New | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 1644/TD | 18/06/2025 | 18/06/2025 | Resource Division | 7.99 | 0 | 0 | 0
Total | [13 empty] | 1002.91 | 188.65 | 18.81