## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | Tilkhoja & Adjoining mouzas | SM/12133 | New | Material Requisition To Resource Division |  |  | RTOR000180/2022-2023 | 2432/TD | 16/01/2023 | 16/01/2023 | Resource Division | 27.95 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Tilkhoja & Adjoining mouzas | SM/12133 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Tilkhoja and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001322/2022-2023 | 2324/W/MMD | 29/12/2022 | 27/06/2023 | BHABANI PRASAD MANNA | 23.7 | 0 | 0 | 60
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | Tilkhoja & Adjoining mouzas | SM/12133 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Tilkhoja PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engiener | ORD/000876/2023-2024 | 198/TD | 10/01/2024 | 20/01/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | Tilkhoja & Adjoining mouzas | SM/12133 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 1570/TD | 23/04/2024 | 23/04/2024 | Resource Division | 14.36 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Tilkhoja & Adjoining mouzas | SM/12133 | New | Quotation for Tilkhoja w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608980, Ref ID-204222618) |  |  | BILL/04498/2023-2024 | BP-2023-24-852 | 16/03/2024 | 16/03/2024 | WBSEDCL | 2.97 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | Tilkhoja & Adjoining mouzas | SM/12133 | New | Quotation for new service connection at Tlkhoja w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App ID 2004685657, Con ID 204277587) |  |  | BILL/00646/2024-2025 | BP-2024-25-123 | 05/05/2024 | 05/05/2024 | WBSEDCL | 9.91 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | Tilkhoja & Adjoining mouzas | SM/12133 | New | Installation of display Board at 5 nos {1. TILKHOJA PWSS,( PUMP HOUSE -1 &2) 2. RADHABALLAVCHAK PWSS ( PUMP HOUSE -1 &2), 3. GOBARDHAN PWSS( PUMP HOUSE -1), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000255/2025-2026 | 61/RWS/TSD | 06/05/2025 | 13/05/2025 | SUDIP MANNA | 0.83 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | Tilkhoja & Adjoining mouzas | SM/12133 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 299.32 | 2.9 | 75
Total | [13 empty] | 10391.27 | 300.28 | 2.89